## Fac & Cap Proj DTL 02-13-18
|  |  |  | Latest Committed Scope/Timeline from UPCD/FacOps | [14 empty] | TBD - Placeholder Est. Timeline | [9 empty] | In Progress |  |  |  |  | Complete
NOT CONFIRMED/DEFINITIVE
|  |  | 2017 | [11 empty] | 2018 | [11 empty] | 2019
Bldg/Area |  | Project Scope | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Academic Renovations:
Drama/Music | w | Ceiling & Lighting Renovation (hallways/common space 1st and 2nd floors)
To finish out phase 1 of the ceiling and lighing renovation effort in the Drama/Music building, work should have commenced during the winter intersession to renovate the popcorn ceiling sections and replace with a flat finished surface. Fac Ops has yet to confirm expected start date. Phase II, consisting of the Music building, was estimated to begin in May 2018 and continue through the summer and fall semesters. Similarly to the Drama Music building, it should have incorporated the replacement of the ceiling, lighting and stair treads to common areas and corridors. Fac Ops has retracted commitment on this project and no plans in the immediate future for renovation.
-> Phase 1a Summer 2017 will include the 1st and 2nd floors of DramaMu building only | bar: 2017 Jun to 2017 Oct
-> TBD; Phase 1b Winter 17/18 Remove/replace popcorn ceilings -DID NOT HAPPEN --> Est. Summer 2018 | bar: 2018 May to 2018 Jun
-> TBD; Phase II to include the 1st and 2nd floors of Music (w/Orch) building - no confirmation from FAC OPS
Drama/Music | w | Ceiling, Lighting & Painting Renovation (interior classroom, performance space and faculty/staff offices)
Issue: Ceiling and lighting in front lobby space, vestibule, rear loading area, common spaces, corridors, green room and back offices are original or near original to the facility. Most of the ceiling tiles are badly stained and warped from age, high humidity levels and/or water damage. Lighting is extremely old, ineffective or defective and inefficient/non-compliant to green standards. Stained wood doors are also original to the facility and show excessive wear and tear as well as paint on walls in many locations. Repair: Complete ceiling and lighting replacement to the lobby space (front and back), back offices and and paint and restoration to the common space walls, corridors and doors.
-> Mike J. Commitment/Timing placeholder (either Summer 2018 or Summer 2019) | bar: 2018 May to 2018 Aug; 2019 May to 2019 Aug
Nafe Katter Theatre | w | Flooding Mitigation Effort - Katter Lobby
-> Regrading & draining project to be complete either during Winter break or Summer 2018 | bar: 2017 Dec
VdM | w | Stage Extension Project | bar: 2017 Jun to 2017 Aug
- Scope included 6' stage extension, matching side staircases and wood paneling to back of stage
-> Planning & Design | bar: 2017 Feb to 2017 Apr
-> Bidding and contract award | bar: 2017 May to 2017 Jun
-> Est. construction start/end (note: est. 3 wks of construction/will not impact Orient. or Confratute 5/18 - 7/14) | bar: 2017 Jul to 2017 Aug
| w | Flooring/Furniture (objective is to phase in around stage extension work) | bar: 2017 May to 2017 Sep
-> New carpet install to front lobby, recital hall and back loading area | bar: 2017 May to 2017 Aug
-> Furniture Upgrade | bar: 2017 Jul to 2017 Aug
-> Casual chairs to be delivered Jan 3 AM | bar: 2018 Jan
-> TBD; Continuation of new carpeting to back office area | bar: 2018 May to 2018 Jul
| w | HVAC upgrades and repairs
- Scope included replacement of existing air handler unit and install of chiller, heat exchanger, rooftop exhaust fans and renovation of mechanical room | bar: 2017 May to 2017 Aug
-> Planning & Design | bar: 2017 Jan to 2017 Feb
-> Bid Requests | bar: 2017 Mar to 2017 Apr
-> Project under review with CPCA; funding and timeline tentative | bar: 2017 May to 2017 Aug
| w | Ceiling and Lighting Renovation Effort | bar: 2018 May to 2018 Aug
->TBD (Deferred Maintenance Request) - Scope to include complete ceiling and lighting replacement to the lobby space (front and back) and back offices. Paint and restoration to the common space walls, corridors and doors. Possible reconfiguration of back offices and light construction retrofit.
| w | Seating Replacement Effort | bar: 2018 May to 2018 Aug
->TBD (Deferred Maintenance Request) - Scope to include replacement and upgrade of auditorium seating and restoration or replacement of existing cement floor.
| w | Replacement of Lobby HVAC units | bar: 2017 Dec to 2018 Jan
-> Planning & Design | bar: 2017 Nov
-> Removal of units | bar: 2017 Dec
-> Floor abatement | bar: 2018 Jan
-> Carpet Installation | bar: 2018 Jan
| w | Video Projector and Screen Replacement | bar: 2018 May
-> TBD; Contingent on SFA budget disposition
| w | Replacement of Auditorium Seating and Resurfacing of Existing Flooring
-> Mike J. Commitment/Timing placeholder | bar: 2018 Jul to 2018 Aug
| w | Ceiling, Lighting and Painting Renovation (Mike J. Commitment)
-->>Ceiling, Lighting and Painting Overhaul - Front lobby and back stage, loading area, green room and back office offices & corridors. Project will be phased due to limited timing over summer months.
-> Phase I: Lobby, Box Office, Auditorium | bar: 2018 Jul to 2018 Aug
-> Phase II: Back Stage, loading area, green room, back offices and corridor. | bar: 2018 Dec to 2019 Jan
Studio/Mobius | w | Installation of new flooring, theatre seating, painting | bar: 2017 Aug to 2018 Feb
-> Planning & Requirements Evaluation | bar: 2017 Jan to 2017 Mar
-> Bidding and contract award (if not in-house) | bar: 2017 Apr to 2017 Jun
-> Est. construction start/end (has to be before or after Sept - Oct)
-> All abatement and restoration complete; waiting for permanent seating to be delivered and installed.
Art Ceramic Studio | w | Installation of exhaust, make-up air unit and duct work/steam coils | bar: 2017 May to 2017 Aug
Music Bldg/Music 102 | w | Accoustic Accreditation Mitigation
-> Planning & Design | bar: 2017 Feb to 2017 Mar
-> RFP Bid Requests (successfully bid/contained within budget) | bar: 2017 Oct to 2017 Nov
-> Renovations complete | bar: 2017 Dec to 2018 Jan
Benton | w | Security Upgrades
-> The Benton Museum has significant security gaps in terms of appropriately securing and monitoring its cultural property. A security assessment meeting was conducted with the Director of Security from Harvard Art Museums, UConn Public Safety, Director of the Benton, SFA Assistant Dean, SFA Dean and UPDC to walk-through and discuss Benton’s current security model, gaps and limitations, review of Harvard Art Museums security strategies, systems and resources. Representatives of Public Safety also toured the Harvard Art Museum galleries to further review best practices and security parameters we could implement at the Benton Museum. A debrief and summarization of security requirements and improvements for the Benton’s future security upgrades were distributed. It is expected that implementation of these recommendations should commence in the summer 2018 timeframe.
-> Assessment Meeting | bar: 2017 Dec
-> Planning & Facility Requirement Upgrades | bar: 2018 Jan to 2018 Apr
-> Est. security modification upgrades start/end | bar: 2018 May to 2018 Aug
| w | Carpeting Upgrades
Carpeting upgrades to the Benton galleries. In scope areas include: Study, Center and East Galllery. TBD areas include: Gilman and the second floor landing.
-> Planning & Requirements Evaluation | bar: 2017 Nov
-> Installation to start June 1 | bar: 2018 Jun
Jorgensen/HSJ | w | Trap Room Water Project
-> Mitigation efforts include: waterproofing, pipe repairs, upgrade of pump system and install of curtain drains; work began on 10/16 to remove 3 upstage traps to allow access into trap room. Project will take 6 - 8 weeks to complete.
-> Planning & Requirements Evaluation | bar: 2017 Feb to 2017 Mar
-> Modification upgrades start/end TBD | bar: 2017 Jul to 2018 Feb
| w | Sound System Upgrade
-> The scope of this project includes a complete sound system upgrade to the Jorgensen's upper auditorium, as well as the lower Harriet S. Jorgensen theatre. Project is with UPDC and currently vetting requirements and evaluating outside consultants for the design/build aspects.
-> Planning & Requirements Evaluation | bar: 2018 Jan to 2018 Mar
-> Bidding and contract award | bar: 2018 May to 2018 Jun
-> HSJ Installation Est. Timeline | bar: 2018 Aug to 2018 Sep
-> Upper Jorgensen Installation - TBD
| w | Lobby Door Restoration Project | bar: 2017 Jul to 2017 Oct
-> FacOps completed the Lobby Door Restoration Project which upgraded the mechanical hardware with new door closers and the replacement of weather-stripping; all doors were also repainted as part of the restoration effort.
| w | Lighting Instruments & Control Board Upgrade Project
-> TBD; Contingent on SFA budget disposition | bar: 2019 Jun to 2019 Aug
| w | Exterior Lighting - TBD
-> Facilities completed lighting survey; upgrading LED lighting on soffit overhang front entryway | bar: 2017 Jul to 2017 Aug
-> Full Installation: TBD
| w | HSJ Flooring Abatement & Replacement Effort
-> Scope to include full asbestos abatement effort and replacement of existing flooring in the HSJ vestible and theatre lobby
-> Planning & Requirements Evaluation | bar: 2017 Nov to 2018 Jan
-> Bidding and contract award | bar: 2017 Nov to 2017 Dec
-> Asbestos Abatement | bar: 2018 Mar
-> Flooring Installation & Renovations will happen either in March or end of July/early Aug | bar: 2018 Mar; 2018 Jul to 2018 Aug
Capital Projects:
UCMB Practice Field | w | Observatory deck, loading dock and storage container unit | bar: 2017 May to 2017 Aug
-->> The Fine Arts Band Tower provides a 40 foot tall permanent observation structure for band conductors to view band practices and preparations. It also serves to improve access to the practice site and provide safe location for loading and unloading band practice equipment.
-> Bidding and contract award | bar: 2017 Feb
-> Fabrication and construction start/end | bar: 2017 Mar to 2017 Jun
Final project close-out | bar: 2017 Nov
Music Library | w | Fine Arts Project - Ground level - Fine Arts Resource Center, 1st Level - Fine Arts Learning/Study Center, 2nd Level - Dean's Office suite
-> The project scope incorporates complete demolition and redesign to the former Music Drama Library building and lobby. The basement level will be maintained as an SFA Resource Center and extension of HBL, circulating music scores, sound recordings, videos, playscripts and stagecraft books. It will contain a circulation desk, one classroom and copy center. circulate music scores, sound recordings, videos, playscripts and stagecraft books. The first floor dedicated as a student study space with comfortable seating, project break-out space and a series of traditional desks. The second floor will be resdesigned into the new SFA Dean's Office space with a combination of open floor plan work space stations, private offices and center conference room. the project is currently in-progress and is anticipated to complete at the end of March. Expected move-in is April 5, 2018.
-> Planning & Design | bar: 2017 Mar to 2017 Jun
-> Bidding and contract award | bar: 2017 Jul to 2017 Aug
-> In Progress; construction start/end | bar: 2017 Sep to 2018 Mar
Production Facility | w | Production facility, main thoroughfare & entryway, utility remapping
-->> The production facility project will encompass a brand new facility addition directly behind the Nafe Katter Theatre. It will serve to provide a new SCENE and COSTUME shop, make available additional teaching spaces and communal areas for students, patrons and other constituents to study, create and explore. And finally, it will act as a major thoroughfare for SFA, physically connecting the Art Building to the Drama/Music complex.
-> Planning, Design & Prep:
- 100% completion construction documents | bar: 2017 Mar to 2017 Apr
- staging of construction area/compromise of Lot 1 Area 2 parking | bar: 2017 Aug
- RFP and selection of Construction Manager at Risk Firm | bar: 2017 Sep to 2017 Dec
- Parking Lot Mitigation - Improved accessibility access to VdM and Drama/Music complex | bar: 2017 Nov
-> Bidding and contract award (extensive) -> to include SFA addendums | bar: 2017 Dec to 2018 May
-> Est. construction start
- site utility work (will affect Bolton Rd, Maple La, Coventry Rd) | bar: 2018 May to 2018 Sep
-->>Site utility project will incorporate major tunneling to reroute and supply new utility lines to the von der Mehden Recital, Nafe Katter Theatre, Studio Möbius Theatre, Drama Music and Music buildings and the Fine Arts building. This will encompass water, electricity, sewer and data lines and intermittently impact all buildings above plus Coventry Rd. and Maple Lane throughout the course of the next six months starting in May 2018. This project will be highly invasive to the entire School of Fine Arts community and take careful planning, communication and execution.
- excavation & foundation | bar: 2018 Oct to 2018 Dec
- major construction, mechanical, electrical, etc. (may extend into Fall 2019 semester) | bar: 2019 Jan to 2019 Aug
Art Building | w | Roof Replacement
The Fine Arts building will undergo a re-roofing effort likely during the summer of 2019, which should incorporate a brand new roof membrane, replacement of leaking skylights and flashing and removal of existing solar panels if the budget permits. Project has now been folded into the Fine Arts Phase II (901667) project. This project will directly impact the Art and Art History department and could significantly impact these specialized areas (namely the art studio classrooms due to the skylights removal and replacement and the second floor faculty offices). Important to consider end user stakeholders and project team to ensure people, furniture, equipment and resources are properly moved and/or secure in advance of this project.
-> Planning & Design | bar: 2018 Apr to 2018 Jun
-> Bidding and contract award | bar: 2018 Jul to 2018 Sep
-> Est. construction start/end | bar: 2019 May to 2019 Sep
| w | Room 105 Renovation
-> New flooring, ceiling tiles, electrical and paint | bar: 2018 Jun to 2018 Jul
***Renovations needed in advance of Fine Arts Phase II for piano lab relocation***
Drama/Music Complex | w | Façade Project -
Project scope will incorporate the replacement of the existing facades to the Drama Music and Music Buildings along RT 195 and Bolton Rd., as well as exterior facades to the interior open courtyard of these buildings. Due to the abatement of asbestos containing material, the replacement of the front skins and the replacement of the HVAC systems of this project will be extremely impactful to all classrooms and offices. Because of this, careful planning, communication and execution will need to occur -- especially as it relates to the coordination of the advanced moving logistics to these specialized spaces (e.g. over a dozen practice rooms will be impacted which contain large, upright pianos).
-> Planning & Design - | bar: 2017 Jan to 2017 Mar
-> Bidding and contract award | bar: 2018 Feb to 2018 Apr
-> Est. construction start/end (lead time for glass/materials is pushing this project out to 2019. Project will be split into two time periods; facades on Bolton Rd. side to be complete Dec/Jan 2019 and facades facing RTE 195 will be complete Summer 2019) | bar: 2018 Dec to 2019 Jan; 2019 May to 2019 Aug
Bishop Building | w | Replacement of Roof & Mechanicals
Issue: Roof is beyond its useful life causing continual water issues and damage throughout building. HVAC and mechanicals are also considerably antiquated and old causing major noise disruption to the lower classrooms, constant maintenance, upkeep and repair issues and perpetual heating and cooling distribution issues throughout the facility. Repair: Needs new roof, HVAC mechanicals and new duct distribution system.
-> Mike J. Commitment/Timing placeholder (either Summer 2019 or Summer 2020) | bar: 2019 May to 2019 Aug
Multiple Performing Areas | w | Energy Conservation Theatrical Lighting Upgrades | bar: 2018 May to 2018 Sep
-> Major LED lighting replacement effort to all of our existing theatres and performances spaces
Space Expansion/Program Relocation
Bishop Center (1st floor) | w | First Floor Space Expansion
Project scope incorporates retrofitting the old Dining Services Administration Office into classroom, lab and faculty office space for our Digital Media and Design program. The construction and renovation effort will take place over the summer 2018 timeframe project and we are in the design phase now of this effort. Again, careful planning and communication will be required to ensure the end user stakeholder (as well as other Bishop programs and end users) are kept up to date on the project scope, critical path and timeline of major milestones of the project.
-> Dining Services relocation | bar: 2017 Jul to 2017 Sep
-> Initial Design Phase | bar: 2017 Oct to 2017 Nov
-> Analysis of Space/Tech Network Requirements | bar: 2017 Dec to 2018 Jan
-> Finalizing Design | bar: 2018 Feb
-> Construction start/end | bar: 2018 May to 2018 Aug
Kirby Mills | w | MFA Art Program Relocation
Kirby Mills Relocation Project - this effort will relocate the existing MFA program from the Depot Campus to the new Kirby Mills location - about 7 miles south of the Storrs campus. Due the disparate location from the main university campus, this will require careful planning with UPDC, UITS, Transportation Services and Facilities to ensure the renovations, move and logistical implications of being off-campus are appropriately covered and supported.
-> Planning & Design | bar: 2017 Nov to 2017 Dec
-> Minor renovations/reconfiguration of floorplan (Est.) | bar: 2018 Jan to 2018 Mar
-> Implement: Signage, Voice/Data Requirements, Security Access, Transportation (Est.) | bar: 2018 Jan to 2018 Mar
-> Move Logistics (Est.) | bar: 2018 May
Wadsworth Antheneum | w | Arts Administration Relocation (TBD)
Project w/ UPDC; Project start: Spring 2018. Scope to include minor renovations/reconfiguration of floorplan, Signage, Logisics plan, Security and Voice/Data Requirements
-> Planning & Design | bar: 2017 Dec to 2018 Jan
-> Move Logistics (Est.) | bar: 2018 May to 2018 Jul
Depot Campus | w | Storage Relocation --On Hold --