## Appendix H - Fac & Cap Proj DTL
[10 empty] | Committed Scope/Timeline from UPCD/FacOps | [37 empty] | TBD - Placeholder Est. Timeline | [8 empty] | In Progress |  |  |  |  | Complete
NOT CONFIRMED/DEFINITIVE
|  |  | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 |  | 2021 | [11 empty] | 2022 | [11 empty] | 2023
Bldg/Area |  | Project Scope | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |  |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Academic Renovations:
Drama/Music | w | Ceiling & Lighting Renovation (hallways/common space 1st and 2nd floors)
To finish out phase 1 of the ceiling and lighing renovation effort in the Drama/Music building, work should have commenced during the 2018 winter intersession to renovate the popcorn ceiling sections and replace with a flat finished surface. Fac Ops has yet to confirm expected start date. Phase II, consisting of the Music building, was estimated to begin in May 2018 and continue through the summer and fall semesters. Similarly to the Drama Music building, it should have incorporated the replacement of the ceiling, lighting and stair treads to common areas and corridors. Fac Ops has retracted commitment on this project and no plans in the immediate future for renovation.
-> Phase 1a Summer 2017 included the 1st and 2nd floors of DramaMu building only | bar: 2017 Jun to 2017 Oct
-> TBD; Phase 1b Winter 21/22 Remove/replace popcorn ceilings -no confirmation from FAC OPS
-> TBD; Phase 2 to include 1st and 2nd floors of Music (w/Orch) bldg-no confirmation from FAC OPS
-> Alternative work order entered to replace missing or damaged ceiling tiles
Drama/Music | w | Ceiling, Lighting & Painting Renovation (interior classroom, performance space and faculty/staff offices)
Issue: Ceiling and lighting in all classrooms, offices and performance spaces are original or near original to the facility. Most of the ceiling tiles are badly stained and warped from age, climate control issues and/or water damage. Majority of lighting is extremely old and defective and inefficient/non-compliant to green standards. Paint in some classrooms shows excessive wear and in many locations. Repair: Complete ceiling and lighting replacement to all classrooms, faculty/staff offices and performance spaces. Targeted painting restoration to needed classrooms.
-> Mike J. Commitment/Timing placeholder (rec'd confirmation not happening Summer 2019)
Drama/Music | w | Photography Darkroom Renovation
Issue: State of darkroom is in disrepair and is not safe due to antiquated enlarger stations, missing and jagged cabinetry, outdated equipment and unsafe lighting equipment Repair: Replace cabinetry, upgrade enlargers, replace sinks, upgrade plumbing and some modification to existing HVAC system.
-> Planning & Requirements Evaluation | bar: 2018 Dec
-> Bidding and contract award (TBD) | bar: 2019 Jan to 2019 Apr
-> Construction start/end (Plumbing, paint, sink installation, and improvement to HVAC) | bar: 2019 Sep to 2019 Dec
-> Construction start/end (Cabinetry upgrades, new sink and drying rack replacement, asbestos removal - behind interior façade, repaint/epoxy floor)
Drama/Music | w | Drama 105 Acting Studio Flooring Replacement | bar: 2019 Dec
--> Project w/ Fac Ops; Scope included included replacement of resilient flooring in Acting studio and polyurethene application.
Drama/Music | w | AC Implementation Project - Music Practice Rooms + Drama Acting Studios
-->Project includes rooftop AC to Drama Acting Studios, plus internal AC units to Music Practice Rooms. Project Est. Start Date - May 2020
-> Planning & Requirements Evaluation | bar: 2019 Nov to 2019 Dec
-> Bidding & Contract Award
-> Construction & Installation - Drama 109, 228, 229
-> Construction & Installation - Music Practice Rooms
Nafe Katter Theatre | w | Flooding Mitigation Effort - Katter Lobby
-> Regrading & draining project to be complete either during Winter break or Summer 2018 | bar: 2018 May to 2018 Jun
-> Mike J. Commitment/Completed Spring 2018
| w | Lobby Renovation & Furniture Upgrade
-> Katter Lobby renovation scope to include new flooring, painting, removal of existing bar, Digital screen upgrade and framed galvanized magnetic poster boards.
-> Planning & Requirements Evaluation | bar: 2019 Nov to 2019 Dec
-> Carpet Installation and paint restoration
-> Furniture Delivery
VdM | w | Stage Extension Project | bar: 2017 Jun to 2017 Aug
->Scope included 6' stage extension, matching side staircases and wood paneling to back of stage
-> Planning & Design | bar: 2017 Feb to 2017 Apr
-> Bidding and contract award | bar: 2017 May to 2017 Jun
-> Est. construction start/end (note: est. 3 wks of construction/will not impact Orient. or Confratute 5/18 - 7/14) | bar: 2017 Jul to 2017 Aug
| w | Front Lobby Asbestos Abatement/New Flooring/Furniture | bar: 2017 May to 2017 Sep
-> New carpet install to front lobby, recital hall and back loading area | bar: 2017 May to 2017 Aug
-> Furniture Upgrades | bar: 2017 Jul to 2017 Aug; 2018 Jan
-> Casual chairs to be delivered Jan 3 AM
-> TBD; Continuation of new carpeting to back office area | bar: 2018 May to 2018 Jul
| w | HVAC upgrades and repairs | bar: 2017 May to 2017 Aug
->Scope included replacement of existing air handler unit and install of chiller, heat exchanger, rooftop exhaust fans and renovation of mechanical room
-> Planning & Design | bar: 2017 Jan to 2017 Feb
-> Bid Requests | bar: 2017 Mar to 2017 Apr
-> Project under review with CPCA; funding and timeline tentative | bar: 2017 May to 2017 Aug
| w | Ceiling and Lighting Renovation Effort | bar: 2018 May to 2018 Aug
->TBD (Deferred Maintenance Request) - Scope to include complete ceiling and lighting replacement to the lobby space (front and back) and back offices. Paint and restoration to the common space walls, corridors and doors. Possible reconfiguration of back offices and light construction retrofit.
| w | Seating Replacement Effort | bar: 2018 May to 2018 Aug
->TBD (Deferred Maintenance Request) - Scope to include replacement and upgrade of auditorium seating and restoration or replacement of existing cement floor.
| w | Replacement of Lobby HVAC units | bar: 2017 Dec to 2018 Jan
-> Planning & Design | bar: 2017 Nov
-> Removal of units | bar: 2017 Dec
-> Floor abatement | bar: 2018 Jan
-> Carpet Installation | bar: 2018 Jan
| w | Video Projector and Screen Replacement | bar: 2018 May to 2018 Jun
-> Upgrade video projector, add remote touchpad functionality and raise screen
| w | Replacement of Auditorium Seating and Resurfacing/Replacement of Existing Flooring | bar: 2018 Jul to 2018 Aug
| w | Ceiling, Lighting and Painting Renovation (Mike J. Commitment)
--> Ceiling, Lighting and Painting Overhaul - Front lobby and back stage, loading area, green room and back office offices & corridors. Project will be phased due to limited timing over summer months.
-> Phase I: Back Offices and Box Office | bar: 2018 Jul to 2018 Aug
-> Phase II: loading area, green room | bar: 2018 Dec to 2019 Feb
-> Phase II: front lobby | bar: 2018 Dec to 2019 Jan
-> Mike J. Commitment/Summer 2018 & Winter 2018/19
Studio/Mobius | w | Installation of new flooring, theatre seating, painting | bar: 2017 Aug to 2018 Apr
-> Planning & Requirements Evaluation | bar: 2017 Jan to 2017 Mar
-> Bidding and contract award (if not in-house) | bar: 2017 Apr to 2017 Jun
-> Est. construction start/end (has to be before or after Sept - Oct)
-> All abatement and restoration complete; waiting for permanent seating to be delivered and installed.
Art Ceramic Studio | w | Installation of exhaust, make-up air unit and duct work/steam coils | bar: 2017 May to 2017 Aug
Music Bldg/Music 102 | w | Accoustic Accreditation Mitigation - Music 102 | bar: 2017 Dec to 2018 Jan
-> Planning & Design | bar: 2017 Feb to 2017 Mar
-> RFP Bid Requests (successfully bid/contained within budget) | bar: 2017 Oct to 2017 Nov
-> Renovations complete | bar: 2017 Dec to 2018 Jan
Benton | w | Security Mitigation | bar: 2019 Jan to 2019 Dec
-> The Benton Museum has significant security gaps in terms of appropriately securing and monitoring its cultural property. A security assessment meeting was conducted with the Director of Security from Harvard Art Museums, UConn Public Safety, Director of the Benton, SFA Assistant Dean, SFA Dean and UPDC to walk-through and discuss Benton’s current security model, gaps and limitations, review of Harvard Art Museums security strategies, systems and resources. Representatives of Public Safety also toured the Harvard Art Museum galleries to further review best practices and security parameters we could implement at the Benton Museum. A debrief and summarization of security requirements and improvements for the Benton’s future security upgrades were distributed. It is expected that implementation of these recommendations should commence in the summer 2018 timeframe.
-> Assessment Meeting | bar: 2017 Dec
-> Planning & Facility Requirement Upgrades | bar: 2018 Jan to 2018 Jun
-> Est. security modification upgrades start/end | bar: 2018 Jul to 2018 Aug
-> Panic alarm installation: 1. Front Entrance Main Desk; 2. Gilman Gallery; 3. Center Gallery | bar: 2019 Jun to 2019 Jul
-> Removal of wood mailbox and rebuild of wall per security assessment (deemed security risk) | bar: 2019 Jan
-> Loading dock door replacement per security assessment (deemed security risk) | bar: 2019 Dec
-> Seal or grille storage room windows per security assessment (deemed security risk) | bar: 2019 Dec
-> Reconfigure elevator floor access per security assessment (deemed security risk) | bar: 2019 Aug
-> Outsource/Procure Security Guard Services | bar: 2019 Feb to 2019 Oct
-> Seal or grille storage room windows per security assessment (deemed security risk)
| w | Flooring Upgrades to Center and East Galleries | bar: 2018 Jun
Flooring upgrades to the Benton galleries. In scope areas include: Study, Center and East Galllery. TBD areas include: Gilman and the second floor landing.
-> Planning & Requirements Evaluation | bar: 2017 Nov
-> Installation to start June 1 | bar: 2018 Jun
| w | Flooring Upgrades to Center and East Galleries
The Accreditation Commission of the AAM is tabling their decision on the museum’s accreditation due to the following concerns that are barriers to the institution’s ability to meet the program requirements, eligibility, and/or the Core Standards for Museums. Specifically, during the tabling period the museum must address the following issues cited and demonstrate that it has met the necessary requirements by April 15, 2022:
-->Ameliorate the safety risk posed by the low railing in the second floor Balcony Study Gallery. Both the museum and University could incur liability for this potentially dangerous and non-ADA compliant fixture.
-->Remedy the security risk posed by customers of the Beanery Café who have access to museum spaces (restrooms, visitor services area, stairs to gallery spaces) when the cafe is open but the museum is not, and no security personnel is present.
-> Planning & Requirements Evaluation
-> Bidding and contract award
-> Renovations (TBD)
| w | Benton Museum Learning Space Redesign
--> Purpose of the project is to enhance our educational mission as well as our student experience
--> A complete redesign of an existing conference room adjacent to the East gallery within the Benton museum. Upgrades will include necessary abatement and new flooring, updated lighting with dimming capability, shelving to display artwork, classroom style furniture and audio and video technology upgrades.
-> Planning & Requirements Evaluation
-> Bidding and contract award
-> Renovations (TBD)
Jorgensen/HSJ | w | Trap Room Waterproofing Project | bar: 2018 Jul to 2018 Sep
-> Mitigation efforts include: waterproofing, pipe repairs, upgrade of pump system and install of curtain drains; work began on 10/16 to remove 3 upstage traps to allow access into trap room. Project will take 6 - 8 weeks to complete.
-> Planning & Requirements Evaluation | bar: 2017 Feb to 2017 Mar; 2017 Jul to 2017 Dec
-> Modification upgrades start/end TBD | bar: 2018 Jan to 2018 Jun
| w | Sound System Upgrade - Upper Jorgensen
-> The scope of this project would include a complete sound system upgrade to the Jorgensen's upper auditorium. Project is currently on hold due to budgetary constraints.
-> Planning & Requirements Evaluation | bar: 2018 Jul to 2018 Sep
-> Bidding and contract award
-> Upper Jorgensen Installation Timeline
| w | Sound System Upgrade - Lower Jorgensen: TBD/Project On Hold Due to Funding
--> The scope of this project includes a complete sound system upgrade to the the lower Harriet S. Jorgensen theatre. Project is currently with UPDC and further information is needed from design/acoustic consultants as to the design and build aspects of the speaker array as well as room acoustics.
-> Planning & Requirements Evaluation | bar: 2018 Apr to 2018 Jun
-> Further evaluation of room acoustics and speaker array design with consultants
-> HSJ Installation Est. Timeline (TBD - No Funding Identified)
| w | Exterior Lobby Door Restoration Project - Upper and Lower Jorgensen | bar: 2017 Jul to 2017 Oct
-> FacOps completed the Lobby Door Restoration Project which upgraded the mechanical hardware with new door closers and the replacement of weather-stripping; all doors were also repainted as part of the restoration effort.
| w | Lighting Instruments & Control Board Upgrade Project
-> TBD; Contingent on SFA budget disposition
| w | Exterior Lighting Upgrade | bar: 2017 Jul to 2017 Aug
-> Facilities completed lighting survey; upgrading LED lighting on soffit overhang front entryway
-> Full Installation: TBD
| w | HSJ Flooring Abatement & Replacement Effort
-> Scope to include full asbestos abatement effort and replacement of existing flooring in the HSJ vestible and theatre lobby
-> Planning & Requirements Evaluation | bar: 2017 Nov to 2018 Jan
-> Asbestos Abatement (TBD)
-> Flooring Installation, Lighting Upgrades & Renovations (TBD)
| w | Jorgensen Card Reader Upgrade
--> Meeting with Rod/Gary/Matt P./Dana Dunnack to assess requirements and system install | bar: 2019 Feb
--> Card Reader installation | bar: 2019 Sep to 2019 Dec
| w | Jorgensen Video Surveillance Upgrade
-->Based on recent security assessment of Jorgensen, Public Safety has agreed to fund the installation of 7 exterior cameras and 10 interior camera placements based on survey recommendation
-> Public Safety performing contractor walk-through | bar: 2018 Oct
-> J. Pirog comparing quote received to sec. assessment needs | bar: 2019 Jan
-> Video camera installation | bar: 2019 Sep to 2019 Dec
| w | Flooring Replacement to Upper Jorgensen and Gallery
--> Scope to include replacement of existing flooring in the upper auditorium and lower Gallery/reception area. Carpet is beyond it's useful life and becoming warped and buckled causing multiple tripping incidences with patrons.
-> Planning & Requirements Evaluation
-> Bidding and contract award
-> Flooring Installation & Renovations - Main Lobby & Auditorium
-> Flooring Installation & Renovations - Lower event space & Gallery
| w | ITS Recabling and Equipment Upgrade (HSJ/CRT)
--> Project to include shielded cabling upgrade to CRTs Harriet S. Jorgensen theatre to address Clearcom health and safety issues. Project Est. Start Date - May 2021
| w | Clearcom Replacement Upgrade (HSJ/CRT)
--> Project includes replacement and upgrade of current theatre operation intercom system. Equipment upgrade necessary to address health and safety issues present in current antiquated system causing high-pitched feedback and interference issues to end user population.
--> Planning & Requirements Evaluation
--> Bidding and contract award
--> Installation of new wireless intercom system
| w | Jorgensen Center Chiller Replacement
--> Project includes rooftop chiller replacement, plus interim cooling during project timeline. Project Start/End Date - May 2020
| w | Jorgensen Freight Elevator Replacement
--> Abatement of floor tiles and prep work to existing area
--> Build out of new elevator technology control access room
--> Upgrade of freight elevator lift system
| w | HSJ Rigging System/Fire Safety Curtain Replacement
--> The current 37-year-old system failed inspection of its fire safety curtain, counterweight line set and light bridge hoist. As noted in the report, based on National Building, Fire, and Safety Codes and ANSI standard, the HSJ, which is the Connecticut Repertory’s main stage theatre, has been deemed unusable since the failure of these components prohibit an audience from attending a performance.
--> Code Evaluation Review
--> Planning & Requirements Evaluation
--> Bidding and contract award
--> Installation of rigging system components
--> Installation of fire safety curtain system
Art Building | w | Contemporary Art Galleries
--> Ceiling/Lighting/Blackout shades | bar: 2018 Jul to 2018 Aug
| w | Split Unit HVAC Unit Installation - ARTB 101 & 102
--> Irregular room temperatures, generally hot and unregulated
--> Install split unit HVAC systems to address climate issues. | bar: 2017 Sep
| w | Mechanical Room Waterproofing
--> Apply floor epoxy to the mechanical room; will significantly reduce or completely diminish any future water penetration to ART105. | bar: 2019 Mar
| w | Drop Ceiling & New Lighting - ARTB 101, 102 & 103
--> Particulate matter from existing ceiling spray foam lingers with the working/learning environment; falls onto students' work and into technology equipment causing damage
--> Install new drop ceilings and lighting to all three rooms
| w | Room 105 Renovation
-> New flooring, ceiling tiles, electrical and paint | bar: 2018 Jun to 2018 Jul
-> Floor epoxy for waterproofing | bar: 2019 Mar
| w | High Powered Computing Lab
--> Convert (2) upper level staff offices to one large lab space
-> Planning & Requirements Evaluation | bar: 2018 Dec
-> Bidding and contract award (TBD)
-> Renovations (TBD)
| w | Krenicki STEAM Design Lab
--> Convert old business office footprint into programming and material resource space for Krenicki STEAM lab
-> Planning, Design & Requirements Evaluation
-> Bidding and contract award
-> Renovations
Bishop Center | w | Bishop Center Enhancements - Custom Lockers & Water Refilling Station
-> Students lack storage to store student materials and supplies; lack of potable water to building community
-> Planning & Design
-> Build & Installation
Multiple SFA Buildings | w | ITS Recabling and Equipment Upgrade | bar: 2019 May to 2019 Sep
(except Ballard) |  | --> ITS to Determine Project Requirements - ITS will take inventory of all existing cabling and network equipment throughout the complex and develop plans and specs for recabling (to Gigabit technology) and upgrade equipment to latest UConn support standards
-> Planning & Requirements Evaluation | bar: 2019 Jan to 2019 Feb
-> Bidding and contract award (TBD) | bar: 2019 Mar
-> Begin recabling effort | bar: 2019 May to 2019 Aug
Multiple SFA Buildings | w | Card Reader Upgrade to Genetec System
--> Project w/ Fac Ops; Project completed Winter 2020. Scope included replacement of card swipe technology to Genetech (proximity) system to multiple exterior/interior SFA doors. | bar: 2019 Dec
--> Converted all remain exterior doors to the Fine Arts building, Drama-Music and Music buildings, Nafe Katter Theatre and von der Mehden Recital Hall, Thomson Building, Art Ceramic Studio
--> Converted multiple interior doors to to critical lab, studios and performing art spaces to improve physical security of assets.
Multiple Performing Areas | w | Acoustical Evaluation Study
--> The purpose of this Study is to evaluate SFA facilities in multiple studio and lab spaces used for music practice, class instruction, film and video studios, and the Harriet S. Jorgensen theatre used for musicals and main stage production of the Connecticut Repertory Theatre. The recommended modifications will be prioritized into short-term and long-term solutions for each problem identified with a focus on addressing accreditation concerns, health and safety and space utilization priority.
-> Planning, Design & Requirements Evaluation
-> Bidding and contract award
-> Study Assessment & Report
-> Renovations
Capital Projects:
UCMB Practice Field | w | Observatory deck, loading dock and storage container unit | bar: 2017 May to 2017 Aug
--> The Fine Arts Band Tower provides a 40 foot tall permanent observation structure for band conductors to view band practices and preparations. It also serves to improve access to the practice site and provide safe location for loading and unloading band practice equipment.
-> Bidding and contract award | bar: 2017 Feb
-> Fabrication and construction start/end | bar: 2017 Mar to 2017 Jun
->Final project close-out | bar: 2017 Nov
Fine Arts Atrium | w | Fine Arts Project - Ground level - Fine Arts Resource Center, 1st Level - Fine Arts Learning/Study Center, 2nd Level - Dean's Office suite
-> The project scope incorporates complete demolition and redesign to the former Music Drama Library building and lobby. The basement level will be maintained as an SFA Resource Center and extension of HBL, circulating music scores, sound recordings, videos, playscripts and stagecraft books. It will contain a circulation desk, one classroom and copy center. circulate music scores, sound recordings, videos, playscripts and stagecraft books. The first floor dedicated as a student study space with comfortable seating, project break-out space and a series of traditional desks. The second floor will be resdesigned into the new SFA Dean's Office space with a combination of open floor plan work space stations, private offices and center conference room. the project is currently in-progress and is anticipated to complete at the end of March. Expected move-in is April 5, 2018.
-> Planning & Design | bar: 2017 Mar to 2017 Jun
-> Bidding and contract award | bar: 2017 Jul to 2017 Aug
-> In Progress; construction start/end | bar: 2017 Sep to 2018 Apr
Production Facility | w | Production facility, main thoroughfare & entryway, utility remapping
Fine Arts Phase II 901667 |  | -> The production facility project will encompass a brand new facility addition directly behind the Nafe Katter Theatre. It will serve to provide a new SCENE and COSTUME shop, make available additional teaching spaces and communal areas for students, patrons and other constituents to study, create and explore. And finally, it will act as a major thoroughfare for SFA, physically connecting the Art Building to the Drama/Music complex.
-> Planning, Design & Prep:
- 100% completion construction documents | bar: 2017 Mar to 2017 Apr
- staging of construction area/compromise of Lot 1 Area 2 parking | bar: 2017 Aug
- RFP and selection of Construction Manager at Risk Firm | bar: 2017 Sep to 2017 Dec
- Parking Lot Mitigation - Improved accessibility access to VdM and Drama/Music complex | bar: 2017 Nov
-> Bidding and contract award (extensive) -> to include SFA addendums | bar: 2017 Dec to 2018 May
-> Construction start
- site utility work (will affect Bolton Rd, Maple La, Coventry Rd) | bar: 2018 May to 2019 Jan
->Site utility project will incorporate major tunneling to reroute and supply new utility lines to the von der Mehden Recital, Nafe Katter Theatre, Studio Möbius Theatre, Drama Music and Music buildings and the Fine Arts building. This will encompass water, electricity, sewer and data lines and intermittently impact all buildings above plus Coventry Rd. and Maple Lane throughout the course of the next six months starting in May 2018. This project will be highly invasive to the entire School of Fine Arts community and take careful planning, communication and execution.
-> Production Facility + main entry/corridor + tie-in to Fine Arts building
- major construction, mechanical, electrical, etc. (TOC est 1/31/20) | bar: 2019 Jan to 2019 Dec
- Procure FF&E | bar: 2019 Dec
- Operational & Transition Logistics
Art Building | w | Roof Replacement
Fine Arts Phase II 901667 |  | The Fine Arts building will undergo a re-roofing effort likely during the summer of 2019, which should incorporate a brand new roof membrane, replacement of leaking skylights and flashing and removal of existing solar panels if the budget permits. Project has now been folded into the Fine Arts Phase II (901667) project. This project will directly impact the Art and Art History department and could significantly impact these specialized areas (namely the art studio classrooms due to the skylights removal and replacement and the second floor faculty offices). Important to consider end user stakeholders and project team to ensure people, furniture, equipment and resources are properly moved and/or secure in advance of this project.
-> Planning & Design | bar: 2018 Jul to 2018 Sep
-> Bidding and contract award | bar: 2018 Nov to 2019 Jan
-> Substantial completion start/end | bar: 2019 May to 2019 Sep
Drama/Music Complex | w | Façade Project -
Fine Arts Phase II 901667 |  | -> Project scope will incorporate the replacement of the existing facades to the Drama Music and Music Buildings along RT 195 and Bolton Rd., as well as exterior facades to the interior open courtyard of these buildings. Due to the abatement of asbestos containing material, the replacement of the front skins and the replacement of the HVAC systems of this project will be extremely impactful to all classrooms and offices. Because of this, careful planning, communication and execution will need to occur -- especially as it relates to the coordination of the advanced moving logistics to these specialized spaces (e.g. over a dozen practice rooms will be impacted which contain large, upright pianos).
-> Planning & Design - | bar: 2017 Jan to 2017 Mar
-> Bidding and contract award | bar: 2018 Feb to 2018 Apr
-> Substantial completion start/end | bar: 2018 Dec to 2019 Jan; 2019 May to 2019 Aug
Bishop Building | w | Replacement of Roof & Mechanicals
-> Issue: Roof is beyond its useful life causing continual water issues and damage throughout building. HVAC and mechanicals are also considerably antiquated and old causing major noise disruption to the lower classrooms, constant maintenance, upkeep and repair issues and perpetual heating and cooling distribution issues throughout the facility. Repair: Needs new roof, HVAC mechanicals and new duct distribution system.
PROJECT ON HOLD DUE TO BUDGET CONSTRAINTS
Ballard Inst. & Museum of Puppetry | w | HVAC Upgrades
-> The Ballard Institute museum space in Downtown Storrs is unable to maintain consistent recommended temperature and humidity standards for a museum space. Museum standards are relative temps between 68-72F and 45-55% humidity throughout the year. Currently, during the winter, the temperature is too high (often above 75F), and the humidity is too low, but with high spikes. During the summer, while the temperature stays around 70-72F, the humidity is too high--usually above 60%. What is necessary is consistency throughout the entire year, without dramatic changes in a short period of time. Even with multiple stop-gap measures in place, the current system is not adequately equipped to meet professional museum standards and is preventing the Ballard from moving forward with the accreditation process. Please see Mike Rocchetti if further information is needed on the interim repairs and modifications that have been made to-date.
-> Discussed scope items with Mike Rochetti (Aug 2018) | bar: 2018 Aug
-> CKB Submitted Project Request (Sept 2018) | bar: 2018 Sep
-> Scoping Meeting of Design of Replacement/Upgrade Effort | bar: 2019 Feb to 2019 Mar
-> LONG TERM PROJECT ON HOLD DUE TO BUDGET CONSTRAINTS
-> Mitigation Scoping Meeting w/ Fac Ops | bar: 2019 Sep
-> HVAC Mitigation Repairs/Short Term Fixes Installed | bar: 2019 Oct to 2019 Dec
Drama/Music Complex | w | Steam Vault & Line Replacement | bar: 2019 May to 2019 Oct
Fine Arts Phase II |  | -> Managed under the Fine Arts Phase II 901667 project
-> Major impact to Coventry Rd, Maple Lane and portions of Bolton Rd (Nafe Katter entrance)
-> On track to begin summer 2019 through October 2019
von der Mehden | w | Roof Replacement
-> Planning & Design -
-> Bidding and contract award
PROJECT ON HOLD DUE TO BUDGET CONSTRAINTS
Multiple Performing Areas | w | Energy Conservation Theatrical Lighting Upgrades
-> Major LED lighting replacement effort to all of our existing theatres and performances spaces; To serve as a model for the rest of the venues, evaluation of Studio/Mobius underway with Facilities Management, Barbizon and Dramatic Arts Master Electrician; updated ROI study & Eversource rebate numbers forthcoming
-> Evaluate fixture replacement requirements for smaller Studio Mobius as a template for other theatres
-> Cost estimate and timeline, inclusive of ROI and any Eversource rebates
PROJECT ON HOLD DUE TO BUDGET CONSTRAINTS
Space Expansion/Program Relocation
Bishop Center (1st floor) | w | First Floor Space Expansion | bar: 2017 Jul to 2018 Aug
-> Project scope incorporates retrofitting the old Dining Services Administration Office into classroom, lab and faculty office space for our Digital Media and Design program. The construction and renovation effort will take place over the summer 2018 timeframe project and we are in the design phase now of this effort. Again, careful planning and communication will be required to ensure the end user stakeholder (as well as other Bishop programs and end users) are kept up to date on the project scope, critical path and timeline of major milestones of the project.
-> Dining Services relocation | bar: 2017 Jul to 2017 Sep
-> Initial Design Phase | bar: 2017 Oct to 2017 Nov
-> Analysis of Space/Tech Network Requirements | bar: 2017 Dec to 2018 Jan
-> Finalizing Design | bar: 2018 Feb
-> Construction start/end | bar: 2018 May to 2018 Aug
Prod Facility (2nd Floor) | w | Alternate 2B - Theatre Studies Offices + Conference Enablement Project
901667 - Altenate 2B |  | -> Project scope incorporates retrofitting (5) faculty offices and conference room space for Theatre Studies faculty; current Theatre Studies/Bishop footprint will become DMD Administration Suite
-> Planning & Design | bar: 2019 Jan to 2019 Apr
-> Construction & Renovation | bar: 2019 May to 2019 Dec
-> Operational & Transition Logistics
Bishop Center (1st Floor) | w | DMD Administration Suite Relocation Project
-> Renovate Bishop Center 101 - 108 offices and conference space to accomodate DMD Administration Suite
-> Planning & Design
-> Construction & Renovation
-> Operational & Transition Logistics
Kirby Mills | w | MFA Art Program Relocation | bar: 2017 Nov to 2019 Jan
-> Kirby Mills Relocation Project - this effort will relocate the existing MFA program from the Depot Campus to the new Kirby Mills location - about 7 miles south of the Storrs campus. Due the disparate location from the main university campus, this will require careful planning with UPDC, UITS, Transportation Services and Facilities to ensure the renovations, move and logistical implications of being off-campus are appropriately covered and supported.
-> Planning & Design | bar: 2017 Nov to 2017 Dec
-> Renovations/reconfiguration of floorplan per approved plans | bar: 2018 May to 2018 Dec
-> Implement: Signage, Voice/Data Requirements, Security Access, Transportation (Est.) | bar: 2018 May to 2018 Jul
-> Punch List Items | bar: 2019 Jan
-> Move Logistics (Est.) | bar: 2019 Jan
| w | MFA Art Program Ventilation Mitigation Project
--> Project consists of ventilation upgrades and paint booth installation to meet EH&S standards. Project w/ UPDC, with no definitive timeline set.
-> Planning & Design | bar: 2019 Feb to 2019 Nov
-> Reassessing the budget and availability of the products
-> Engage an engineer to review and consult on the electrical, fire protection and installation requirements.
-> Construction & Renovation Projected Start/End
PROJECT ON HOLD DUE TO BUDGET CONSTRAINTS
Wadsworth Antheneum | w | Arts Administration Relocation
-> Project w/ UPDC; Project start: Spring 2018. Scope to include minor renovations/reconfiguration of floorplan, Signage, Logisics plan, Security and Voice/Data Requirements
-> Planning & Design | bar: 2017 Dec to 2018 Mar
-> Construction & Renovation | bar: 2019 Sep to 2019 Dec
-> Operational & Transition Logistics
Depot Campus | w | Museum Storage Relocation from Depot Campus - TBD
-> Benton, Ballard and Historical Costume Collection open-access museum collections storage, resource and research center relocation needed from current location at Depot Campus
-> Planning & Design | bar: 2019 Nov to 2019 Dec
-> Construction & Renovation (TBD)
-> Move Logistics
PROJECT ON HOLD DUE TO BUDGET CONSTRAINTS
Kirby Mills | w | Art Annex --Kirby Mills
-> The proposed “art annex” would be used as a multipurpose flex space to host public exhibitions, performance art and joint installations for each of the respective museum collections. The annex would also serve as a co-collaboration and study space for MFA, arts administration, costume design and puppetry faculty and students for various lectures and/or integral class instruction.
-> Planning & Design
-> Construction & Renovation (TBD)
-> Operational & Transition Logistics