## Cover Sheet
School of Fine Arts Facilities Issues Master Documentation Last Updated: 2/13/20

## SFA Dean's Office
SFA Dean's Office
| Priority | Description |  | Area/Building/Room | Status
1 |  | Cleaning request white tile façade |  | Orchestra Building | Completed
| 2019-10-08 |  | Front façade of the orchestra building (facing 195) tile looks moldy Mike will assist what needs to be done, some cleaning to protect the paint Aris working on who/what to get up
| 2019-01-02 |  | Planning to power wash in the spring
| 2020-02-13 |  | In progress: scheduled for spring (when it's warmer)
| 2020-10-07 |  | Per Nate - Power Washed in June.
2 | S | "Do not clean" faculty office |  | Art Faculty Offices | Completed
| 2019-10-08 |  | Address the do not clean faculty offices, notice mold in ceiling tile John Richardson emailed faculty/staff that the university will recommence cleaning faculty offices on second floor of the Art Building - approximately once a month CKB: sent Aris "SFA do not clean list" CKB: to f/u regarding the mold - possibly a rountine annual mold inspection within academic and performing spaces
| 2019-10-31 |  | Routine mold inspection cannot happen, unless condition present themselves will not check for mold, schedule separately if necessary
| 2020-02-13 |  | James will double check, N.Bedard will check for doormats
| 2019-10-08 |  | Due to cars, salt, and weather condition there are cracks in the cement - can be dangerous for patrons and students - especially at night facilities offered to places a pot (rock) to block the path for cars and remove during snow removal. However that path is necessary for the March band for unloading and loading equipments - heavy equipments are not easy to go down the path. Not predictable when they will need access Considering to give a notice when to move the rock/pot aside and once finished to move it back f/u meeting to further discuss on November 7th between CKB, N.Bedard, Eric Rice
| 2019-01-02 |  | Gravel has been installed rock/pot will be installed by end of the week 1/4/20
| 2020-02-13 |  | Plows moved plants, moved back Glenn mentioned to not move. Stone has been graveled in Work with parking services, to give tickets to those who are parked there Next step need signage > patron only
| 2020-10-07 |  | "Complete" in the sense that facilities is cleaning the space.
3 | ILT | Card reader system problems |  | Fine Arts Buildings | Completed
| 2019-10-08 |  | Moved into current space a year and half ago, Genetec (new version) was installed having issue with updating card, locking, individual not having access Music Department is on the older system, Millennial (only swipe) Determine subsequent meeting current configuration across SFA complex Training strategy SFA solution to streamline card reader system Alishaa to schedule meeting between Nate. B, Dana Dunnak, Rick O'Toole, CKB, Stacy Webb, Michael Toomey, Alishaa, Andy Kelly
| 2019-10-31 |  | Two doors in front façade - custodial/maintenance has the master key, music department would like to have access - don't know who to contact to get access
| 2019-12-12 |  | Rick, Alishaa, DMD and Music attended Gentec Training Genetec installed on 12 other doors in the Music rooms to convert away from Millenium
| 2020-02-13 |  | There were a power outrage at the production facility determining rather it was a power issue or system issue. Nisha Hardnett & Bob Copley received training on Genetec, Bob was able to get Genetec up and trying to figure out the details (will reach out to Dana if have any issues). Michael Toomey joined the training again, has a better understanding Ed worked with Colleen and Alishaa to get genetec setup for the Production Facility - everything seems to be running smoothly
| 2020-10-07 |  | This should be resolved. Kate will check with Nisha to confirm.
| 2020-10-15 |  | No current issues. Kate continues to work with Dana Dunnack and in Genetec to troubleshoot access issues. KP
4 | S | Radiator cover replacement |  | DRMU Buildings | Completed
| 2019-10-08 |  | Radiator covers need to be placed back ASAP CKB or AH to put WO in if they see radiator covers not on
| 2020-02-13 |  | Radiators are loosely fitted, needs to be refixed 231

## Art & Art History
Art & Art History
| Priority | Summary Description |  | Area/Building/Room | Status
1 | S | Electrical wall outlets short circuiting |  | Art Building Studio Spaces | In Progress
| 2017-10-06 | WO: 726362 - closed | Building is maxed out. Could we possibly integrate new electrical system within infrastructure on production facility
| 2017-03-23 |  | New and/or upgrade of eletrical system is not feasible at this time. Colleen recommends that a project proposal should be at least be prepared to evaluate and assess scope, time and cost. 5 yrs plan
| 2017-03-27 |  | Lighting - a comprehensive list of all lighting issues is included in a seprate document. This list contains the same issues and concerns that were generated by a walkthrough that occurred in fall 2016, that is not yet resolved
| 2017-10-20 |  | FacOps is aware of classroom lighting issue and is slowly working to address.Colleen to follow with Cora Lynn and Jay to evaluate progress based upon Arts issue list
| 2018-11-01 |  | All rooms have been replaced with new LED lights. Room 109 continues to be an issue. Track lights may be incompatiable with new LED to be addressed with J. Johnston
| 11/16/18 - 4/18/19 |  | Need resolution to room 109
| 2019-09-19 |  | In progress: FacOps to follow up - N. Bedard to follow up with the Electrical shop
| 2019-10-31 | WO: 143809 | In progress: N. Bedard to get update from Ray DiCapia
| 2020-01-02 |  | Complete as of 12/28/2019
| 2020-02-13 |  | N.Bedard to get WO notes
| 2020-10-07 |  | Kate to check Charlene to see if this is still and issue.
| 2020-10-15 |  | Per Charlene No current issues reported. Kate noted to submitt work orders if any issues arise. KP
| 2022-05-01 |  | Walkthru conducted with FA. Stakeholders determined that the issue was caused by space heaters because the building was not producing enough heat. HVAC to repair heat units in each room and electrical is adding an outlet in each room.
| 2022-11-17 |  | Per Nate: Half the spaces have been completed. Facilities is waiting on wiring for the remaining spaces. KP
2 | ILT | Units are extremely loud, and entirely disruptive to use during class. |  | Art Building | Completed
| 2016-10-06 |  | Units are often turned off simply to be able to have class lectures and critiques. Students work, instead in coats, hats and scarves Jay & Cora Lynn completed walkthrough to review classrooms affected. Jay completed w/o to have these rooms fixed
| 2017-03-23 |  | (Cora Lynn) Heating units in ARTB #108, 111, 112, 113: the usual issues remain the units are so loud when running that facility routinely choose to turn them off in order to deliver lecture material or conduct critiques. You cannot, otherwise hear anything. When the units are running the noise considerable but students can at least be more comfortable. In order to hear, though, students must bundle up to work. This is unacceptable
| 2017-03-27 |  | Dave Garside - switch install rooms 108, 111, 112, 113 heating units - switch lower so step stool isn't needed
| 2017-10-20 |  | Thermostats should be moved lower for access. If possible, replace these units completely. The same issues remain. Poor temperature control and impossible noisy to hold class if the units are running. Rm. 109 is unbearably hot. Back doors cannot be opened without moving out the huge partitions. Circulation is achieved by turning up the thermostat (so it thinks we want the room warmer). As long as the heat is not on that will circulate air, but with no cooling or de-humidifying. Fall classes have been unbearable. M. Bock reports that #116 NEW system was apparently continually breaking down last spring. Not sure where that stands now. Colleen inquired if units can be replaced with remote thermostats. Eric Kruger to evaluate, Colleen to follow up
| 11/1/18 - 4/18/19 |  | Unresolved; need updated from facilities
| 2019-09-19 |  | In progress: FacOps to follow up; HVAC Mgr concerned it turned off – pipe can freeze, age at unit need to be replaced. Do we want to invest in unit solve problem with old unit or just replace. Glen’s decision – need a specific time and funding update
| 2019-10-31 |  | In progress: N. Bedard to get update from Glenn
| 2020-01-02 |  | In progress: Glenn would like to set up a walk through
| 2020-01-21 |  | Alishaa to send Colleen AAH issues to address with John Richardson
| 2020-02-13 |  | Alishaa sent over to Charlene to get an update
| 2020-10-15 |  | Per Charlene No current issues reported. Kate noted to put in a work order for any issues that arise when campus ramps back up. KP
| 2021-10-01 |  | If new issues arise W/O will be placed. KP
3 | ILT | Continous roof leaks across multiple rooms |  | Bishop Print Shop, lowest level (basement) | Completed
| 2016-10-06 |  | Leaking ceiling across multiple rooms (some with hi-tech equipment): May begin to drop again - bowing as we speak. The roof leaks continously. The leaks often come through the light fixtures, forcing us to turn off that row of lights. Leaks through the tiles ruins tiles and threatens expensive cameras. Covering the stop motion work spaces will not work (will ruin the shot) Restoration of patching/sealing has concluded. New individual leaks will be addressed with new w/o
| 2017-03-23 |  | Update 3.24 (Cora Lynn) Though this is ongoing from prior reports, there are new leaks in the ceiling. The decision has been made to not report the new leaks to Facilities. They are in the hallway and remedied by bucket placement. Plugging up the leaks only results in leaks in new areas. We have determined the devil we know (hallway) is better than the devil we don’t (unknown location of new leaks- possibly over irreplaceable technological equipment)
| 2017-10-20 |  | This situation is ongoing and worsening. See separate account (additional document). Carissa will send to Eric K., Jay Dave K. Patching has been completed. Recommend to pls. continue to report leaks to create document of issues
| 2018-11-01 |  | Unresolved; still in progress. Patching and repairing in place until Bishop roof replacement occurs. Continue to report leaks and document issues. Close-out on Facilities Issues Document; Bishop Center roof replacement converted to a UPDC project. Per Aug 2018 meeting with UPDC (M. Groza), roof to be replaced summer 2020; current scope includes replacement of roof membrane and replacement of HVAC/mechanicals.
| 11/16/18 - 4/18/19 |  | Roof project on hold indefinitely. UPDC to confirm latest timeline
| 2019-09-19 |  | In progress: FacOps to follow-up with UPDC to determine latest estimate on roof/mechanical replacement.
| 2019-10-31 |  | N.Bedard to do a walkthrough with Prof. Laurie Sloan
| 2020-01-02 |  | E-mailed Lauire Sloan asking to set up a walk through
| 2020-02-13 |  | N.Bedard walked the space with Laurie Sloan Water seems to be good/active, stains still there Laurie to submit a WO, N.Bedard to check
| 2020-10-07 |  | Check with Laurie to 1. See if it was completed or get work order # and Nate will follow.
| 2020-10-15 |  | Kate noted that department should put in WO for any issues that arise. KP
| 2021-10-01 |  | Spoke with Laurie Sloan. No current leaks. Ceiling tiles should be replaced where leak was. Asked department to add a work order to have ceiling tiles replaced. KP
| 2022-04-28 |  | Facilities Recommends putting in Work Orders as required. DD
4 | ILT | Due to excessive Noise, Central Air Unit/Mechanicals on Roof |  | Bishop, 2nd floor | On Hold
| 2016-10-06 |  | Central air unit is noisy: constant continous hum. Place sound attenuators on the vents on the roof? This is a top issue - people can't concentrate to work, communicate or hear presentation/films/critics/ unless this noise can be reduced. At the very least - find out which specific elements are causing the noise - ventilation, air conditioning, heating, other electrical systems. Maybe the sound can be dampened before replacing the roof begins (which could be some time out). Continual noise at this level may be injurious to students and employees See notes on roof replacement within Bishop
| 2017-10-20 |  | Also ongoing - see additional document. Carissa wil send to facilities. There are blue items that appear to dampen noise
| 2018-11-01 |  | Unresolved; still in progress. Excessive noise will continue until Bishop roof/mechanical replacement occurs. Update 11/1/18: Continue to report and document issues. Close out on Facilities issues document; Bishop center converted to a UPDC project. Per August 2018 meeting with UPDC (M. Groza), roof to be replaced summer 2020; current scope includes replacement of roof membrane and replacement of HVAC/mechanicals
| 11/16/18 - 4/18/19 |  | Roof project on hold indefinitely. UPDC to confirm latest timeline
| 2019-09-19 |  | Unresolved: FacOps to follow-up with UPDC to determine latest estimate on roof/mechanical replacement
| 2019-10-31 |  | In room 209 leak in roof work with workshop, smells musty and mold but there's no mold
| 2020-02-13 |  | Mitigation plan in place, 209 add notes
| 2020-10-07 |  | Per Nate, they walked the roof, major cap project. Smaller things have been done to fix minor issues to fix leaks and improve noise. Reach out to M. Tumey to see if they are still having any issues.
| 2021-10-01 |  | Place W/O as issues arise. KP
5 |  | Exterior Framing & Siding |  | Art Cermaic Studio | Completed
| 2017-10-20 |  | Looks much better since the paint job, but the rotting wood particularly where dirt and leaves pile up around the foundation is defeating the new paint job
| 11/1/18 - 4/18/19 |  | Unresolved; need update from Facilities.
| 2019-09-19 |  | In progress: FacOps to follow up with Carpentry Shop
| 2019-10-31 |  | Wes filled lanscape with gravel
| 2020-01-02 |  | Sofit replaced and drained gutter to be relocated by 1/10/2020
| 2020-02-13 |  | Check to see if still dealing with, check with Monica
| 2017-10-20 |  | Damp room - peeling is being evaluated for lead content depending on results, work order is in place for appropriate patching and repainting of damp room over winter term Currently being addressed by Jon Cooke & the paint shop
| 11/1/18 - 4/18/19 |  | Unresolved; need update from facilities
| 2019-09-19 |  | In progress: peeling paint was led base from mock test, still being evaluated - landscape email - Colleen will take lead
| 2019-10-31 |  | Might need mold test and replace what we need
| 2019-01-02 |  | Monica f/u with Jon Cooke on 12/12/19, might have been resolved In progress: N.Bedard to f/u
| 2021-10-01 |  | In process. N.Bedard checking current status.
| 2022-04-28 |  | Per Nate, work order inserted for pavement/stone and will get resolved. Siding issue has been patched for all exposed holes. Waltham will do periodic animal checks. Place Work Orders as issues arise. Mitigation strategy in place for resolution.
6 | ILT | Track and spot lights issue |  | ARTB115 | Completed
| 2019-10-08 | WO: 190930 - 128097 | Track and spot lights issues light emitted on buzzing sound when turned on
| 2019-10-31 |  | N.Bedard to f/u
| 2020-01-02 |  | Work order closed/complete
| 2020-02-13 |  | Recently closed in early January.
7 | S | Faulty light center outside 216 |  | Bishop Hall Outside of 216 | Completed
| 2019-10-08 | WO: 190806 - 113223 | Light sensor not working outside 216. The sensor blinks and registers movement, but the hall lights do not turn on f/u with N.Bedard
| 2019-10-31 |  | N.Bedard to f/u
| 2019-12-12 |  | Alishaa to follow up with Charlene
| 2020-01-02 |  | closed 10/26/2019
| 2020-02-13 |  | N.Bedard to add WO notes
| 2020-10-20 |  | Complete KP
8 | S, ILT | Drop ceiling proposal |  | ARTB 101, 102, 103 ceiling | Completed
| 2019-10-08 |  | Decrease the particulate matter the existing spray foam installation generates. This matter lingers with the working/learning environment as it falls onto students' work and into equipment Allowed a drop ceiling, there is stains and leaks, screws that are visible. 600-700 square ft Junk of installation came down, potential breathing hazard - not ideal environment possible solution: fireproofing panels Will get a better sense of project after roof is complete, will put workorder estimate for drop ceiling in Art Studio (101-103)
| 2019-12-12 |  | CKB to enter project request
| 2020-02-13 |  | Project request submitted: #142325
| 2020-10-19 |  | Colleen to place new project order. KP
| 2020-10-19 |  | Colleen placed new project order. KP
| 2021-10-01 |  | Project Complete. KP
9 |  | Irregular room temperature |  | Art Building Rm 101 | In progress
| 2017-03-23 |  | Occupants attempt to regulate temperature by opening the exterior door, which leaves the space too dirty (dead leaves, etc) to be used as a clean room for photography Art will plac without and Dave will follow up - 102 and 103 split system
| 2017-10-20 |  | Split HVAC units have been installed in 102 & 103. Cleaning staff have been given access from AAH to clean rooms. Ceiling tiles damaged during installation (in the new hallway/lobby ceiling) have not been repaired/replaced. A work order went in immediately, near the beginning of the semester. Eric K to follow up
| 11/1/18 - 4/18/19 |  | Unresolved; need update from facilities
| 2019-09-19 |  | Unresolved: Need update from FacOps
| 2019-10-31 |  | Dan Buttrey: still on list, no new work order in, is the problem solved or outstanding issue?
| 2019-12-12 |  | Walkthrough with Nate, Glenn, and Pete
| 2020-01-02 |  | Nate I'll need to set up a walk through can someone in the department put in a work order?
| 2020-02-13 |  | Ask Charlene to place WO in
| 2020-10-20 |  | Charlene to place WO as issues arise. KP
| 2022-05-25 |  | John mentions issue is not rectified and has a similar issue in 102 now. Facilities to work on this
| 2022-06-09 |  | Nate to inquire on whether department chooses to have controls to regulate temp; Nate to enter WO if needed.
| 2022-11-17 |  | Possible WO needed: Evaluate source of issue. Nate did walk thru on 11/17/22. Details to follow.
10 |  | Punch list from renovation |  | First Fl Art Building | Completed
| 2017-10-20 |  | a. Door painting - needs to be gray b. Hall gallery - rubber tile replacement c. Lighting for gallery walls, specs called for 6, each bay only has 4 installed d. Missing cable locks replacement e. Exposed wires need to be tidied up
| 2017-10-20 |  | Door have been painted but not the frames. Carissa entered another work order per FacOps request to complete frames, not yet complete Additional heads were installed in the hallway gallery bays - this is positive. They do not match the original heads and therefore, give off a different color light than the exisiting heads. This is not positive. Someone came to work on the exposed wires today (10/17). Results unknown. Rubber tile replacement has not taken place. Colleen to work with Dave Koehler to address
| 2018-11-01 |  | Update 11/1/18: Door frames painted/complete. Still need rubber tile replaced for Hall Gallery space: C Bridgeman to have further follow up is needed for Dave Koehler
| 11/16/18 - 4/18/19 |  | Unresolved; need update from facilities
| 2019-09-19 |  | Unresolved: Need update from FacOps/Department
| 2019-10-31 |  | f/u with John
| 2019-12-12 |  | Need to confirm color with the dean - CKB to f/u
| 2020-02-13 |  | Hold until further noticed
| 2020-10-20 |  | Nate needs paint color from Colleen. Project has been put on hold. KP
| 2022-05-25 |  | John agreed this can be closed out. May look into removing the tile in the future
11 |  | Inconsistent Cleaning |  | All Art Buildings | Completed
| 2017-10-20 |  | Art 118: Sink needs to be professionally cleaned Art 119: Sink needs to be professionally cleaned, special w/o needed because of chemicals to clean sink Art 120: Needs soap dispenser and sometime damp mopping (once per week, as per ceramics lab). Should be regularly stocked with paper towels. Colleen to discuss with Jay - should we enter WO for additional custodial requests?)
| 11/1/18 - 4/18/19 |  | Unresolved, need update from facilities
| 2019-09-19 |  | Unresolved: Need discussion with Department to allow custodial staff access to faculty offices for routine cleaning; this will also help to monitor and control possible mold issues in the future
| 2020-01-02 |  | Should be resolved please e-mail if there are issues
| 2020-02-13 |  | Alishaa emailed Charlene to confirm
| 2020-10-20 |  | Issue resolved. Charlene will place work orders as needed. KP
12 |  | HVAC System for Building Environment |  | Art Building | On Hold
| 2018-11-16 |  | Not all of the air handlers on the roof are working and the air intake has been diminished to lower the fan noise, however CO2 monitors and measurements are not working correnctly. Thermostats are also inoperable There is an upcoming roof project occuring this summer; however in the interim, Facilities will look at the air intake with regards to CO2 and revisit the thermostats
| 2019-03-07 |  | Meeting with DH and HVAC in progress
| 2019-04-18 |  | Per 2/19 meeting with DH and facilities , HVAC mechanicals will continuned to be maintained and not replaced as part of the roof project scheduled for summer 2019
| 2019-09-19 |  | Unresolved; Need update from FacOps: Nate Bedard to follow up with HVAC to revisit mitigation plan
| 2019-12-12 |  | N.Bedard to reconfirm with Glenn
| 2020-02-13 |  | Nate to ask if there's any issues up there
| 2021-10-02 |  | In progress. Nate checking noise issues. KP
| 2022-11-17 |  | Kate emailed Nate for update.
13 | ILT | Restoration of mechanical room |  | Second floor Mechanical Rm (Above 105) | Completed
| 2016-04-07 |  | The parts are supposed to be in the mechanical room in the second floor but are not installed. On 4/7/16 (based on recent walkthrough): Work has been going on in the Mechanical Room. What have they done to fix the leaks? The ceiling MUST go. Damaged beyond damaged
| 2016-10-06 |  | This classroom will be submitted to the Classroom Committee for upgrades. Leaking from the mechanical room. Water around the floor, drain isrotted out-matches ceiling tile. W/O has been closed, Jay will find out if there is a plan to fix it
| 2017-03-23 |  | Has this been submitted to the classroom renovation committee? Can only use this room as storage in its present state. Needs: re-lamping, leaking ceiling fixed, new carpet (or no carpet), paint, new ceiling. Equipment/furnishings needed: Tables & Chairs; Enlarger; Trimmer; Lockable cabinets; Shelving
| 2017-10-20 |  | Leak is fixed: Jay will work with Pete to fix/replace all items to have classroom functional before semester begins. Additional time will be needed to move pianos to this room before 1st day of classes. Colleen to follow up with Cora Lynn regarding moving logistics plan
| 2018-11-01 |  | J. Johnston coordinating with T. Haskell regarding move out. Jay will coordinate renovations. Water penetration in space should be rectified before renovations begin. Renovations to include: replacement of ceiling tiles as necessary, painting and installation of floor eletrical outlets for eletric pianos/keyboards. Update 11/1/18: Close-out on facilities issues document - project complete
| 11/16/18 - 4/18/19 |  | Project completed; Closed out see 11/1/18 notes
| 2019-09-19 |  | Completed
| 2019-12-12 |  | Mechanical replace barrens caused a flood, N.Bedard to f/u regarding action about mechanical closet
14 | O | CAG Restoration |  | Contemporary Arts Gallery | Completed
| 2017-03-23 |  | Track lighting is fincky and ancient. CAG needs a new ceiling (an open metal grid). Facilities estimated (last summer, 2014? 2015?) $9,000 would cover the cost of an attractive ceiling grid, some new track lighting and moving the light switches into the CAG. Currently, David Koehler is our contact This is a public space. Derek and Peter will look into this memo
| 2017-10-20 |  | Project request form will be submitted. See additional document for details regarding CAG space *** Colleen to enter project request
| 2018-11-01 |  | Unresolved; C. Bridgeman entered project request as of 2/19/18. Update 11/7/18 - per DH, J. Richarson, gallery received new LED lights, a drop ceiling and curtains. This needs can be removed from the deferred maintenance list
| 11/16/18 - 4/18/19 |  | Project completed closed out. See 11/1/18 notes
| 2019-09-19 |  | Completed
15 |  | Photography Darkroom: ventilation issue |  | DRMU Building | Completed
| 2017-03-23 |  | Can have it evaluated, fluff/buff DRMU – June 15th
| 2017-03-27 |  | FacOps can have it evaluated during DRMU ceiling renovation
| 2017-10-20 |  | See additional document for details regarding Darkroom space. Colleen to enter project request. Please communicate with janet Prichard & Dan Buttrey for dark room needs
| 2018-11-01 |  | Unresolved: C. Bridgeman entered project request as of 2/19/18. Update 11/1/18. In progress – project scope is being prepared by department head; further review with COO and Academic Renovations once requirements are vetted
| 11/16/18 - 3/7/19 |  | Unresolved; need update from facilities
| 2019-04-18 |  | FacOps has agreed to a revised renovation summer 2019 schedule inclusive of: (1) minor modications (partially remove interior partition in 115B) to the advanced lab area to accommodate a longer/deeper sink (2) plumbing repair to address pressure and temperature issues, (3) secure dividers on workstations in advanced lab, (4) replace door seals to film processing rooms, (5) evaluate HVAC reliability and adequacy, (6) relocate eyewash shower closer to front of room, (6) paint room 115.
| 2019-09-19 |  | Resolved: FacOps completed phase I renovation summer 2019 schedule inclusive of: (1) minor modications (partially remove interior partition in 115B) to the advanced lab area to accommodate a longer/deeper sink (2) plumbing repair to address pressure and temperature issues, (3) secure dividers on workstations in advanced lab, (4) replace door seals to film processing rooms, (5) evaluate HVAC reliability and adequacy, (6) relocate eyewash shower closer to front of room, (6) paint room 115.
16 |  | Consolidate HVAC 105 Mechanical Room |  | Art 105 | Completed
| 2018-11-16 |  | Water instrusion originating in Mechanical room above space. Piano lab is moving back into this space during the winter session and concerned about continual leaks to the space, restitution for items lost and the accessibility of space going forward Additionally, ruining some sheet music and perhaps damage to electric pianos; facilities
| 2019-03-07 |  | Jay to confirm - Waterproofing to begin during spring break week
| 2019-04-18 |  | Waterproofing complete
| 2019-09-19 |  | Complete
17 |  | Lack Temperature Control |  | Bishop Print Shop | Completed
| 2016-10-06 |  | Temperature control is non-existent: Large Print shop space (#2), letterpress space (#3), and Silkscreen Lab (#12): Temperature are far too cold, summer through winter. There's no local control of the temperature in any of printmaking spaces. DMD spaces share this issue (though their rooms are too hot - ours are too cold). It is difficult to work in this otherwise useful space and this space is used daily by Art and Art History students and faculty See notes on HVAC concerns within DMD
| 2017-03-27 |  | John & Laurie have reported this OK
| 2017-10-20 |  | Laurie Sloan reports this is largely resolved in the printshop spaces (cannot speak for DM)
| 11/1/18 - 4/18/19 |  | Completed; closed out
| 2019-09-19 |  | Complete
18 |  | Water infiltration issue |  | Art Ceramic Studio | Completed
| 2016-10-06 |  | Water seepage during rain: regarding needed around building to stop water flow into first floor when it it rains. This problem was corrected at McMann but neglected at ACS Still an issue Rick talked to Bob Fl. Will regrade area
| 2017-03-27 |  | Grading outside and Bob Flowers
| 2017-10-20 |  | Eric K. talked to Bob Flowers about re-grading area to reduce water flow into 1st floor
| 11/1/18 - 4/18/19 |  | Unresolved, need update from facilities
| 2019-09-19 |  | Resolved: redirected downspount to stop water flow into ACS: water now filtered away from building
19 |  | Landscaping |  | Art Ceramic Studio | Completed
| 2017-10-20 |  | Landscaping, Broken Asphalt and Litter around the building continues to be a huge problem. The poison ivy by the back entrance has been kept under better control, but everywhere else around the perimeter is a dump. The new fence around the transformer on the south side of ACS prevents mowing or weed control, & the loose gravel is washing away to great ruts where the steam pipes has to be dug a couple of years ago. I notice large stone gravel has replaced unmanageable grassy area by the roadside leading to McMann & ACS. Replacing all the weedy dirt around the parameter base of ACS would be a good solution. We've also never been able to count on daily litter pick up around the building, no matter how often we request it. Enter WO to remove poison Ivy, Aris manages greenspaces
| 11/1/18 - 4/18/19 |  | Unresolved, need update from facilities
| 2019-09-19 |  | Area around ACS landscaped with Stone to eliminate ongoing lawn and weed maintenance issues
| 2022-04-28 |  | Per Nate, work order inserted for pavement/stone and will get resolved.
20 |  | Art building roof damage |  | ARTB Roof Access - Interior Wall surrounding door | Completed
| 2019-10-08 |  | Damaged due to construction project
| 2019-10-31 |  | No visible damage
| 2019-12-12 |  | Rare door was in progress, completed
21 | ILT | Print shop rusty water |  | Bishop Print Shop | Completed
| 2017-10-06 |  | Rusty water is paper soaking sink, turns brown on the edges. Instructors bring in water from home for some projects including all visiting artist projects. This is unacceptable for working print shop Facilities believes this was resolved with a new filter. Cora Lynn will check with Laurie Sloan to confirm it is no longer a concern. - continously rusty discolored RO unit
| 2017-03-23 |  | Filter has been installed. Will need to be replaced due to the nature of use. Place work order when replacement filter is needed.
| 2017-03-27 |  | Dave Garside-rusty water Bishop CT water to do evaluation
| 2017-10-20 |  | This issue remains-turns paper brown. The filter has not worked. Colleen to follow up with Jay
| 11/1/18 - 4/18/19 |  | Unresolved; need update from Facilities.
| 2019-09-19 |  | In progress: FacOps changed filters as of 09/20/19 and will plan to change out every 3 months. Assoc. Professor Sloan to monitor and report water quality.
| 2019-10-31 |  | N.Bedard to follow up with Prof. Laurie Sloan to get an update on the water quality
| 2020-01-02 |  | E-mailed Lauire Sloan asking if the water quality has improved
| 2020-01-10 |  | Walked the Space with Lauire Sloan confrimed filter system has resolved issue
| 2020-02-13 |  | Three month period not issue anymore, resolved per N.Bedard and Laurie Sloan
22 | S | Return and Reinstallation of Storage cage |  | ARTB105 | Completed
| 2019-10-08 | WO: 181009 - 060674 | Already moving forward on - in good shape
| 2019-10-31 |  | N.Bedard to f/u
| 12//12/19 |  | Don schedule for next week construct and plan to workout
| 2020-01-02 |  | Work complete
| 2020-02-13 |  | Closed WO on 1/2/20
23 | ILT | Faulty thermostat |  | ARTB 105 | Completed
| 2019-10-08 | WO: 180924 - 057278 | Room is either too hot or too cold. Thermostat doesn't work Work order status is closed, but thermostat still doesn’t work. Only resolution is to use a switch on a blower which may have Closed on the second day after open - issue is ongoing but not resolved Glen Mathieu - will check status on it f/u with Nate and the work order sign off - get a better timeline and information
| 2020-01-02 |  | December 17th repaired and tested closed/complete work order
| 2020-02-13 |  | Need to add notes from WO

## Dramatic Arts
Dramatic Arts
| Priority | Summary Description |  | Area/Building/Room | Status
1 |  | Add Gender Neutral/Lactation Room Bathroom |  | Drama Music Building | On Hold
| 2021-04-15 | Project Request Entered | Convert one bathroom (RR1A) to a singular bathroom stall (gender neutral); convert the other bathroom (RR1B) to a dedicated lactation room.
| 2021-10-02 |  | Project Pending Funding Source.
| 2021-10-02 |  | In the interim, we will plan to designate the Multipurpose Room (K110) in the new production facility as a wellness/lactation room for the academic year.
| 2022-04-28 |  | On hold indefinitley due to budget regarding gender neutral bathroom. Lacation room is all set, see above
2 | ITL | HVAC Proposal |  | DRMU 128, 227,228 | Completed
| 2017-10-20 | WO: M771313 | Roll away units requested, similar to work in 228. No power in classroom for window-wall hookup. In the case of classroom 128, Drama would be responsible for $1200, facilites would cover the cost remaining of installing the split-system*. This would inclue getting electrical power to that side of the room. (* per HVAC, roll-away may not be ideal for this room, a split-system may be more efficent.)
| 2018-11-16 |  | Project has been transferred to UPDC within Fine Arts Phase II project. Split unit system to be installed and will provide conditioning to the following rooms: DRMU 128, 227, and 228
| 2019-03-07 |  | Project has been transferred to UPDC within Fine Arts Phase II project. Split unit system to be installed and will provide conditioning to the following rooms: DRMU 128, 227, and 228
| 2019-04-18 |  | Project has been transferred to UPDC within Fine Arts Phase II project. Split unit system to be installed and will provide conditioning to the following rooms: DRMU 128, 227, and 228
| 2019-09-19 |  | In Progress: AC study in progress; SFA has requested a whisper quiet split unit system unit. Installation targetted from Winter Session as an early milestone (best case), otherwise units will be installed during the summer 2020 (worst case).
| 2020-02-13 |  | Sunny sing in progress
| 2020-10-20 |  | Completed Summer 2020 by Facilities KP
3 |  | Hallway Lighting |  | Studio theater | On Going - Need update from department
| 2017-10-20 |  | Dimming is needed for performances. Will need fire marshall agreement for code and egress requirments (Jay will help with this), dimming could be controlled through bluetooth option for saftey. Colleen to follow up. Erik K suggested dimming system could be way to add remote controlled LED lights vs wall switches. Add WO after building inspector signs off
| 11/16/18 - 3/7/19 |  | NA
| 2019-04-18 |  | Issue not rectified; issue needs follow up with drama and facilities
| 2019-09-19 |  | In Progress: FacOps to provide samples of new blackout removable pannels for entrance/egrass doors. They are also checking on dimmer capability into Studio Thearte hallway
| 2019-12-12 |  | Very doable, place workorder for billing purposes, will give an estimate shouldn't be more than few $100s.
| 2020-01-02 |  | Nate: we can install dimmer switch. this would be billable would need someone from your department to place work order
| 2021-10-02 |  | Colleen attended meeting to look at the space. KP Colleen add possible update here
| 2022-04-28 |  | Per Nate B, dimmer switch can be installed. Department needs to enter workorder to initiate work effort. This would be billable to the department. ~$250-500 total cost.
4 | ITL | Dust Collection System |  | HSJ Theater | On Hold
| 2019-03-07 |  | Per Jay, need to know if vendir provided sketch is sufficient for installation and permit; need to to determine who will install. Jay to follow-up with Glen Mathieu and Mickey Gorman
| 2019-04-18 |  | Issue rectified; project complete. Close out w/ facilities
| 2019-09-19 |  | In progress: under review with EH&S
| 2019-12-12 |  | Installation meeting discussion to be rescheduled
| 2020-01-02 |  | Need to set up a follow up meeting
| 2020-01-22 |  | f/u meeting scheduled for 1/29/20
| 2020-02-13 |  | Ed was unable to attend f/u meeting, therefore will need a f/u meeting, met kick it off business office Alishaa is working on scheduling
| 2020-10-20 |  | Nate needs update from Colleen on meeting with building inspector with regards to a dust collection system purchase. KP
| 2022-04-28 |  | Delayed due to COVID; meeting needs to occur with Nate Bedard and Ed Weingart to enable project work.
5 | S | Access Issues/Lockbox |  | DRMU Room 105,103,128,228 (Acting Studios) | Completed
| 2019-10-08 |  | Key lock box broken and key stolen. Needs swipe access to the doors for safety and access control for Drama students
| 2020-02-13 |  | Check with 232, keybox slot available, it would be $3K a door Facilities offered to pay for automatic keybox since it would be beneficial for them N.Bedard to send Colleena picture to have a virtual idea
| 2020-10-19 |  | Facilities used exsisting Lock Box. Nate reviewed current lockbox with Kate. Nate can provide additional information on options. KP
| 2021-10-02 |  | Card Reader installed RM 228, Lock Box Demo Meeting Scheduled with Colleen, Kate and Dana Dunnack. KP
| 2021-10-08 |  | Lock Box being priced as part of larger key project. KP
| 2022-04-28 |  | Genetec added to all doors. DD
6 | ILT | Installation of A/C unit |  | DRMU 109 | Completed
| 2019-10-08 | WO: 190924 - 126390 | Window A/C unit to be put in window. The electrical work was completed however the A/C has not been placed on yet. Currently, the A/C unit is on the floor
| 2020-01-02 |  | Nate: Can someone confirm this is still wanted and place a work order
| 2020-10-20 |  | Unit Installed on 9/1/2020 - Complete KP
7 | ILT | HVAC system issues |  | DRMU 101-105 | Complete
| 2019-10-08 |  | HVAC system is not working properly to cool the room WO order was closed even though issue was not resolved, will put another WO in Glen Mathieu will f/u on Alishaa to schedule a meeting between Michael Bradford, Glen Mathieu, Nate Bedard, CKB, Peter McQueeney
| 2020-10-20 |  | New work order needed if issue is still happening. KP
| 2022-11-02 |  | Checked in with Drama, per Dylan, fall went well. No issues. Will reassess during spring semester. Intial issue marked as closed. New W/O will need to be enter if new issue arise. KP
8 |  | Floor replacement - during winter break |  | DRMU 105 | Completed
| 2019-10-08 |  | N.Bedard to circle back with Pete Dunnack
9 | ITL | Energy Consultation & Theatrical Lighting Upgrade |  | HSJ Theater | On Hold
| 2016-10-06 |  | Mike Demers, stage electrician, has been researching this. Been in touch with Stan Nolen. Will work to incorporate all performing areas into a grant. Will also connect with Kirk Matson regarding writing grant for replacement lighting. Could be pushed to UPDC depending on scope. Cost benefit analysis will need to be completed. 60% would be rebate
| 2017-03-23 |  | Mike has toured ECSU's theaters and recital hall where they have many of these LED fixtures currently installed. LED concerns - the lights contains fans, so they make noise. Mike was able to find that the fans are on thermostats and even then they can be overridden by the controls in the control room. Sara Willey, a sales rep with Barbizon lighting, has been invited to come to the Katter theater to give a LED demo. Current fixtures will be hung so group can look at them in a "shootout " manner. All areas will be attended to ensure LEDs will work for their space. The demo data should be solidfied within a week
| 2017-10-20 |  | Project is ongoing - funding is the issue. Established that light from LED noise wouldn't impact performances. Mike Demers - applying for Eversource grant to pay for the upgrade
| 11/16/18 - 4/18/19 |  | Mike D. is in progress of completing an updated engineering study, which would require the following information compiled: 1. the installation cost for each location of the equipment we wish to purchase 2. Number, wattage and type of existing fixtures use (on average) for each location 3. Number of operating hours a year for existing fixtures at each location 4. Number, wattage and type of new fixtures for each new location Follow up meeting with: Energy management, Capital Budget & Planning and Provost Office are required once study is complete and cost benefit is reevaluated
| 2019-09-19 |  | Unresolved: CKB to follow up w/M Demers to determine status
| 2022-04-28 |  | Unresolved: on hold due to budget
| 2022-11-17 |  | CKB checking with Facilities Operations: Incandescent bulbs for these fixtures are no longer being made. In addition, some fixtures utilize glass gels which are also no longer being produced. Once our current inventory of these incandescent bulbs/glass gels is liquidated, the old incandescent lighting fixtures will become obsolete.
10 | ITL | Shades Mitigation |  | DRMU 109 | Completed
| 2016-10-06 | WO: M765887 121670 | Shades fell down and were not reinstalled
| 2017-10-20 |  | Blinds are reinstalled, are light and allow too much sun into classroom which disrupts use of smart board projector. Enter WO for blackout shadde install
| 2018-11-16 |  | Need update from Dramatic Arts to see if the issues has been rectified
| 2019-03-07 |  | Need update from Dramatic Arts to see if the issues has been rectified
| 2019-04-18 |  | Need update from Dramatic Arts to see if the issues has been rectified
| 2019-09-19 |  | Unresolved: Nate Bedard to follow up with FacOps to see if room darkening film material can be applied to windows
| 2019-12-12 |  | N.Bedard sent request for update
| 2020-01-02 |  | Nate: Confrimed that work order was assinged. called tech and left a message for an update. work order assinged 12/12/2019
| 2020-10-15 |  | Completed
11 | S, IPE | Lobby restoration proposal |  | HSJ Theater | Completed
| 2017-10-20 |  | Flooring replacement & repainting needed, Colleen, Pete, Jay, Eric will walk through to assess the scope of project for asbestos floor. Lobby is free between Nov-April. *Colleen to follow up with Jay
| 2018-11-16 |  | Project on hold indefintiley. Need update from Facilities to understand when this will be rescheduled.
| 2019-03-07 |  | Project on hold indefintiley. Need update from Facilities to understand when this will be rescheduled.
| 2019-04-18 |  | Project on hold indefintiley. Need update from Facilities to understand when this will be rescheduled.
| 2019-09-19 |  | Unresolved: Dean working with Provost Ofc for complete HSJ Renovation effort
| 2022-04-28 |  | Jen P is doing abatment for asbestos removal. SFA is moving forward with flooring replacement, paint, and reupholstering theatre doors to the house.
12 |  | Handicap Accessible gender neutral bathrooms |  | Nafe Katter & Studio theater | On Hold
| 2017-10-20 |  | Project Request Form for this project. Converting bathrooms within red hallway - will need to confirm all measurments for ADA compliance. Might be a good opportunity to incorperate a lactation room.
| 2018-11-16 |  | Follow up needed w/Drama -- these bathrooms have multiple bathroom stalls
| 3/7/19 - 4/18/19 |  | N/A
| 2019-09-19 |  | Unresolved: CKB to follow up w/ UPDC to confrim status
| 2022-04-28 |  | On hold indefinitley due to budget
13 |  | Trap Room Water Project |  | HSJ Theater | Completed
| 2016-10-06 |  | Directly below the stage, groundwater is seeping into this area and waterproofing upgrades ar eneeded to ensure water is sent to an area it can be pumped out of the building. A pipe was hit during attempt to remedy the initial issue
| 2017-03-27 |  | A design firm has been hired to engineer solution. With CRT summer season soon underway and the stage being needed for Fall productions, project must be completed within the summer break or held off depending on the length anticipated for the project. Hole doesn't compromise integrity structure, install pumps in 30 days (roof drain has been unclogged)
| 2017-10-20 |  | Work began on 10/16 to remove 3 upstage traps to allow access into trap room. Project will take 6-8 weeks to complete. Drama will need assistance moving materials into trap room and relocating once project is complete. Storage units will be funded by DRU. Piping repairs with mechanical contractor. Nov will be floor portion.
| 2018-11-16 |  | Renovation in progress
| 2019-03-07 |  | Renovation in progress
| 2019-04-18 |  | Project complete and shelving installed close out with facilities
14 | S | Mitigation for dehumidifer Issue |  | Jorgensen Costume Shop | Completed
| 2016-10-06 |  | 2nd industrial dehumidifer died last summer and been replaced with wall hook up This will be a major concern with upcoming summer and 2nd industrial dehumidifier is crucial to handle moisture output, mold has resulted in past.
| 2017-03-27 |  | An air quality assessment was put into w/o (m720872) but closed as they determined the A/C was working without a test being completed
| 2017-10-20 |  | Costume Stock Room has been renovated: Flooring has been abated and replaced. De-humidifier has now plumbed to wall drain. Costumes are being dry cleaned and treated by Battison's. They're being returned weekly as dry cleaning is completed
| 2018-11-16 |  | Project complete. Close out w/ Facilities.
| 2019-03-07 |  | Project complete. Close out w/ Facilities.
| 2019-04-18 |  | Project complete Close out w/ Facilities.
15 | ITL | Shades mitigation |  | DRMU 101 | Completed
| 2016-10-06 |  | Appropriate shades needed on West windows so that classes are not blinded by the afternoon sun and will also block afternoon heat
| 2017-03-27 |  | Enter WO's to have shades repaired
| 2017-10-20 |  | Not installed yet
| 2018-11-16 |  | Issue rectified. Close out w/ facilities
| 2019-03-07 |  | Issue rectified. Close out w/ facilities
| 2019-04-18 |  | Issue rectified. Close out w/ facilities
16 | A,IPE | Flooding in lobby |  | Nafe Katter theater | Completed
| 2017-10-20 |  | Flooding occurs in the lobby when rain storms occur; grading outside allows water to pool and flood; concern that mold will occur from the repetitive flooding: Colleen to request EHS complete a mold assessment of the lobby. Part of defferred maintencance project list. Lawn needs draining to prevent flooding *Colleen to follow up
| 2018-11-16 |  | Issue rectified. Project complete. Close out w/ facilities
| 2019-03-07 |  | Issue rectified. Project complete. Close out w/ facilities
| 2019-04-18 |  | Issue rectified. Project complete. Close out w/ facilities
17 |  | Storage Mitigation |  | Department Storage | Completed
| 2017-10-20 |  | Maria Groza-showed 3 spaced on depot campus near ball field for storage in Nafe Katter near Production Facility
| 2018-11-16 |  | Temp storage provided on Depot Campus. Items will be relocated once Production Facility is completed
18 |  | Theater Access/ Locking issue |  | Studio Theater | Completed
| 2018-11-16 |  | Main doors to the theater do not lock. Newly renovated double doors On-Going; Facilities noticed this issue has been over-looked. They have placed a new work order and indicated this as a security concern. Facilities will have a locksmith over today to see what can be rattified.
| 2019-03-07 |  | OK; Complete per B.Copley
| 2019-04-18 |  | Issue rectified; project complete. Close out w/ facilities
19 |  | Katter Lobby flooring issue |  | Nafe Katter Theater | Completed
| 2018-11-16 | WO was placed | Landing step leading to the Katter Lobby has peeling rubber that needs to be replaced. New item; work order placed. Facilities to follow up
| 2019-03-07 |  | Colleen brought Jay to tripping hazard area of the Nafe Katter; Jay to follow up
| 2019-04-18 |  | Need update from facilities to see if issue has been rectified
| 2022-04-28 |  | Katter lobby underwent complete restoration. Issue recitified
20 |  | HVAC Study & Mitigation Plan |  | DRMU 101 - 105, 242 - 268 | Complete
| 2022-03-10 |  | Facilities Operations & Department met to tour and review HVAC issues throughout multiple studios and office spaces in the Drama Music building. Need detailed assessment and mitigation plan from Fac Ops on how these areas and issues will be addressed. For discussion during next Facilities Advisory meeting scheduled on 05/24/22
| 2022-05-19 |  | Need update from Fac Ops
| 5/24/2022 (CKB Update 06/09/22) | 284751 & 284758 | Add weather stripping to exterior door in DRMU 101. Nate added workorder to evaluate currnet conditions. Door has enough weather stripping and adding further weatherstripping would impede utilizing door for emergency egress.
Please add functionality to exisiting switch that controls the HVAC unit. Department needs a longer lasting off effect (currently they have to hit the switch multiple times to continually stop the HVAC unit). Nate to follow up with HVAC shop to determine options that could be installed and present to Department.
Working on solution to insulate unit to dampen/mitigate noise to HVAC unit in DRAMU 103 and 105. Lift system attempted did not adewuate resolve issue. Nate to follow up w/ HVAC shop. CKB 06/09/22
Room 103 - 105: HVAC Unit has been insulated to reduce sound. Exisiting unit cannot be modified to better control humidity. Can investigate cost and scope to install a dehumidifier for the space. HVAC staff would like to see room during summer to see humidity levels in most impactful months. CKB to follow up w/DH to see if dehumidfiers running in the summer months would be a detrimate to the program. the units would help to dehumidify the space in the most impactful months of the summer, which would help to preserve resilient flooring.
109: HVAC Unit has determined that the PTAC AC unit wont work for this space. Mark has worked with inhouse team to design a multi split system with compresser on roof. Design is complete, waiting for estimate. 06/09/22: Nate to follow up w/HVAC team to determine cost.
242-268: HVAC has turned off heat for summer. While heat is off, HVAC will install a outside air temp rest to control volume of heat sent to radiators. Scheduled for installation in July/August. If this doesn't help, HVAC will work on removing fins and insulating section of pipe. 06/09/22: Nate to follow up to HVAC team to see if project is still on track. CKB
Mobius: Nate is working with Andy Kelly to set up a walk through with life saftey vendor to determine alternative solutions; 06/09/22 - Nate is working with Andy Kelly Nafe Katter: HVAC has not yet looked at changing the register in the theatre. 06/09/22 - Nate to follow up w/ HVAC team.
21 |  | Smoke Alarm Noise in Studio/Mobius Theatre |  | Studio Mobius Theatre | On Hold
| 2022-11-17 |  | Smoke alarm make a humming noise…..Andy noted that it would be an 80k project to change the system out.
| 2022-11-17 |  | On hold indefinitley due to budget

## Music
Music
| Priority | Description |  | Area/Building/Room | Status
1 |  | Acoustician Services |  | Music Building/Practice Rooms | In progress
| 2021-04-15 | Project Request Entered | Based on NASM accreditation report, the current acoustical treatments are inappropriate in the Music Practice rooms. We need to engage an acoustical firm to study the issue so that we may pursue a low-cost solution.
| 2021-08-30 |  | Acoustician services still needed. KP
| 2021-08-30 | Blinds Installeed | Blinds installed in music practice rooms - east bank of practice rooms have had blinds installed to help with temperature and sound. KP
| 2022-04-28 |  | Acoustical study was complete. Mitigation of recommended renovations are in progress. Meeting to review results with department in progress.
| 2022-11-17 |  | Facilites developed a program to address issues related to the study. Program has $50k annual budget. Project order TBD.
2 | S | Need for security assessment |  | Music Basement | Completed
| 2016-10-06 |  | Security cameras needed in remote spaces -Window cutouts needed for studio doors -Help call button -Any future projects to be incorporated with security -Any new camera installed or renewed has to be OK'd with Chief of Police
| 2016-10-06 |  | Andrew Langlais is point of contact within Uconn police. Colleen will meet with him to assess basement security and work on resolution Colleen and Dr. Rice met with Andrew Langlais to review security concerns for the Music Basement in the fall status update and assessment report requested; TBD
| 2017-03-27 |  | Colleen will follow up with Andrew Langlais regarding Music basement Eric Rice - music storage tour through post commencement
| 2017-10-20 |  | Andrew Langlais is no longer with the University. Eric Rice needs to address with Hans Rhynhart and Mike McCue, cc: Eric Kruger, Colleen B MLIB Basement Orchestra Band basement; area is basically sound proof with many hidden corners and is a security nightmare
| 2018-11-01 |  | C.Bridgeman in discussion with Detective Hanna; requesting a security assessment of identified space and mitigation plan
| 2018-11-16 |  | There are current no windows or cameras in this space. It does not feel safe or secure. Would like to discuss additional lighting or security cameras. Contact Detective Hanna to have him tour the space and provide a security assessment
| 2019-03-07 |  | CKB to follow up w/ Public/Safety/Emergency Management
| 2019-09-19 |  | In progress: CKB following up again with Public Safety
| 2021-03-08 |  | Security and Safety Inspection Form Filed - KP
| 2021-08-30 |  | Install of fixed megapixel camera in the elevator lobby of the basement - KP
| 2021-08-30 |  | Install card reader in elevator to secure basement - KP
3 |  | HVAC within lobby issue |  | Von der mehden | Completed
| 2017-10-20 |  | HVAC Unit replaced within the auditorium confirmation of replacement of lobby units for Summer 2018
| 2018-11-01 |  | Per facilities: Lobby units cancelled; per Mike Rochetti: we need to install some sound attenuators on the ducts leading to the 4 rooftop exhaust fans serving the main recital hall. The job would probably be under $20k. CKB to follow up
| 2018-11-16 |  | Project on hold indefinitely; need update from facilities
| 2019-03-07 |  | Project on hold indefinitely; need update from facilities
| 2019-09-19 |  | In progress: FacOps to follow up - N.Bedard to follow up with Mike Rocchetti
| 2019-12-12 |  | Kurt to place a workorder in when fails and have to restart with details to determine the issue
| 2020-01-02 |  | Nate: currently viewed as an improvment project no funding.Have staff submit work orders for any current issues
| 2021-07-11 |  | Per Kurt: Will place W/O as needed. - KP
4 | ITL | Lost/Missing/Sound Panel |  | Music Building | Completed
| 2018-11-16 | WO: 057287 - Completed | Sound panels are missing from various locations in the Music Building; extra panels are stored in the dead file and harp rooms; need to determine where to install and cost Needs to identify space where panels should be installed and put in a subsequent work order
| 2019-03-07 |  | per Eric Rice; someone from facilities came and spoke to Jessye about the sound panels and getting them reattached
| 2019-09-19 |  | Unresolved: need update from FacOps
| 2019-12-12 |  | f/u with Hannah Gebhard
| 2020-01-02 |  | Work order for this was marked complete 3/23/19 can you confirm that this is still and issue?
| 2020-10-20 |  | Completed KP
5 | ITL | Cardswipe access proposal |  | MusB 229 | Completed
| 2018-11-01 |  | Requesting card swipe access to this room as it is currently being used as a rehearsal space and classroom and is currently only accessible by key May need to discuss replacement of door arrangement in order for card swipe access to work properly. Colleen wishes to take this dicussion offline and speak with Dana about electronic access
| 2019-03-07 |  | CKB to follow up with DH and discuss funding for this project
| 2019-09-19 |  | CKB to follow up with DH and discuss funding for this project
| 2020-01-02 |  | Genetec has been installed on 6 Music rooms
6 | S&A | Proposal to remove scaffolding/soffit overhang |  | Music | Completed
| 2017-03-23 |  | Soffits will not be replaced until façade project is completed. Colleen would like safety assessment completed by engineer to ensure that they are of sound and will not collapse before façade project is completed. Front overhang facing 195 should also be assessed for safety integrity concerns
| 2017-03-27 |  | Soffits - Eric Kruger committed to have staging installed on all soffits - will send engineer to have evaluated -New Business: in vdm, concrete overhangs are crumbling. Kirk can see rebar
| 2017-10-20 |  | Eric Kruger put on list. Not façade project
| 11/1/18 - 11/16/18 |  | Unresolved: need update from FacOps
| 2019-03-07 |  | Unresolved: need update from FacOps
| 2019-09-19 |  | Unresolved: need update from FacOps
| 2019-10-08 |  | CKB to f/u with Nate Mike Jednak to discuss with Laura Cruikshank (master planner design/construction)
| 2020-01-02 |  | Nate: planning for this to be done in the spring, scaffolding to be picked up
| 2020-10-20 |  | Per Nate: Complete KP
7 |  | Replace Doors in Classrooms |  | DRMU | In progress
| 2020-01-02 |  | Get new doors for classrooms with standard windows Alishaa to check the floor plan for DRMU and count amount of doubles, include double doors CKB to f/u via email to N.Bedard
| 2021-09-01 | NOTE: | Colleen would like standard maple/single slot window for all of music and drama. Cost/funding dependent project.
| 2022-04-28 |  | Nate will do a walkthrough and access and get quotes. May tie into acoustical study. Nate suggests putting in a work order for estimate for a quote.
8 | S&ILT | Need for additional storage space |  | Music Ensemble Rooms/von der Mehden | In progress
| 2017-03-23 |  | Storage capacity for instruments and/or partition capability to easily access or store away instruments. VDM - storage capacity is inaccessible w/o ladder. Safety concerns for removing & adding instruments to storage in this location Goal is to do for design for summer. Walk through will be coordinated with Eric Kruger, Colleen Bridgeman, Eric Rice and Maria Groza (will add to po castle (vdm contractors)
| 2017-03-27 |  | Eric Rice & Maria Groza will have tour current music storage after commencement
| 2017-10-20 |  | Will include into large meeting with Anne & Maria
| 11/1/18 - 11/16/18 |  | Unresolved: C. Bridgeman scheduling meeting with M. Groza
| 2019-03-07 |  | Unresolved; C.Bridgeman scheduling meeting M. Groza
| 2019-09-19 |  | Unresolved; C.Bridgeman scheduling meeting M. Groza
| 2020-01-02 |  | CKB to f/u with Maria on storage room
| 2022-04-28 |  | Unresolved; C.Bridgeman scheduling meeting M. Groza
9 |  | Ceiling and lighting renovation upgrade proposal |  | Music Building | On Hold
| 2017-10-20 |  | Ceiling & Lighting replacement - confirmation of renovation for summer 2018
| 2018-11-01 |  | Per facilities: A. Ristau working on this - Tom M is PM - schedule is for summer 2018; need update from facilities
| 2018-11-16 |  | Project on hold indefinitely; need update from facilities
| 2019-03-07 |  | Project on hold indefinitely; need update from facilities
| 2019-09-19 |  | Project on hold indefinitely; need update from facilities
| 2020-01-02 |  | N.Bedard to get an idea when it'll happen
| 2022-04-28 |  | N. Bedard will check on status/funding
10 | ILT | Acoustical issue |  | Ensemble Rooms Rm 102 | Completed
| 2017-03-23 |  | Jaffe Holden Report - upgrade of sound dampening drapery - major ensemble rooms In progress - project request submitted; Dave Koehler in process of providing project cost and scope for acoustical/sound dampening resolution Progress has been minimal on project; timeline and scope still TBD. Resolution is critical for upcoming accreditation in 2018. This issue was sited on the last accreditation and cannot go unresolved again
| 2017-10-20 |  | Project is proceeding forward w/ Academic Renovations. Target timelines is winter intersession Out to bid. Tuesday with contractor walkthrough 10/24 diff time of year, Dave is hoping that it will produce
| 2018-11-01 |  | Completed; closed out
| 2019-03-07 |  | N/A
| 2019-09-19 |  | N/A
| 2021-03-17 |  | Per Glen, dampening drapery assessment was completed and Glen will provide outcome as part of the reaccreditation citing noted above.
| 2022-05-12 |  | This will be addressed in the acoustical study. KP
11 |  | Freight Elevator Hazard |  | von der Mehden | Completed
| 2017-03-27 |  | Potential hazard of 10.5" gap between the upstage edge of the lift car and the garage door to access the 1st fl. Lift is used frequently to trainsport 9' Steinway (1200 pounds). If the piano is pushed too far upstage, a caster could run of the lift car and cause a "teeter tooter" action and force the downstage edge of the piano to lift. If anything is between the header and piano, it would be crushed (a head or body part). Appears fixable with removable kick rails to be placed on the cars edges. Project request form was submitted in February Otis visited VDM on 3/23/17
| 2017-10-20 |  | Elevator is fixed. Project completed, cable jumped, heavy/swing - gate struck open. Stephanie Marks is Otis contact
| 2018-11-01 |  | Completed; closed out
| 2019-03-07 |  | N/A
| 2019-09-19 |  | N/A
12 |  | Carpet replacement effort |  | von der Mehden | Completed
| 2017-10-20 |  | Carpet replaced within lobby and auditorium office area needs to be completed, which was a part of a PO. Colleen to follow up with Jay
| 2018-11-01 |  | Completed: part of VDm renovation project over the summer/winter 2018/2019
| 2019-03-07 |  | N/A
| 2019-09-19 |  | N/A
13 |  | Elevator Issues |  | Elevator outside MusB 102 | Completed
| 2018-11-16 |  | The floor indicator light is not working and the elevator is jerky in movement In need of servicing as students utilize this elevator for transporting large instruments
| 2019-03-07 |  | OK; Complete per E. Rice
| 2019-09-19 |  | N/A
14 |  | Water Infultration Issues |  | Music Building; First Floor and Basement | Completed
| 2019-03-07 |  | OK; Complete per E. Rice
| 2019-09-19 |  | N/A
15 |  | LED Light Issues-Too Dim |  | ZFA 103 | In progress
| 2022-05-25 |  | Eric brought up this issue in the Facilities Operation Meeting. Lights are progressivley getting dimmer & dimmer overtime. Stan Nolan will send a crew out to check the dimmers first, believe lights still should be putting out full capacitiy still. Facilities to follow up and put in a WO
| 2022-06-30 |  | Nate to f/u with Stan on progress.
| 2022-10-21 |  | As a temporary solution, electrical shop added to high bay lights to space. Parts for LED lights are back ordered. Will update as parts come in. KP
16 |  | VDM HVAC & Louvers issue |  | VDM | On Hold
| 2022-05-25 |  | Eric brought up this issue in the Facilities Operation Meeting. Louvers on roof open and close on its own on a windy day creating a lot of noise and a hole in the roof. Facilities to assess and try to clamp the vent fan somehow. They will put a WO in
| 2022-06-30 |  | Department requested that louvers be addressed during the roof project. UPDC/Jim Libby to confirm. As of Fall 2022, vdM roof project temporarily on hold.

## DMD
Digital Media and Design
| Priority | Description |  | Area/Building/Room | Status
1 | ILT | Lockers installed |  | Bishop | In progress
| 2019-10-29 |  | Have lockers installed in Bishop just like the Art Building so students can have space to hold their items instead of going back and forth from the Art Building
| 2020-01-02 |  | Nate: need work order and location and sizes CKB, N.Bedard, Heather, Mike V. - discuss at the Bishop f/u meeting - to be scheduled in February
| 2022-05-12 |  | Nate to set up meeting with Department of Corrections to come to campus and provice and estimate
| 2022-06-30 |  | Nate will set up a walkthru to discuss addition of the lockers. Mike Toomey would be the DMD contact for the walk thru. Kate to organize the meeting/walk thru. Lockers in the lower level of Bishop.
| 2022-11-02 |  | Walk Thru completed. Quote prepared and sits with Colleen for approval. KP
2 |  | Replacement of ceiling tiles |  | Bishop 146 | In progress
| 2017-03-27 |  | Colleen will complete walkthrough with Aris to review ceiling tile concerns
| 2018-11-01 |  | C. Bridgeman performed walkthrough of 146 with Aris Ristau during the spring 2018; Unresolved; need update from facilities
| 2018-11-16 |  | TBD; Need to confirm w/ facilities
| 2019-03-07 |  | TBD; Need to confirm w/ facilities
| 2019-09-19 |  | In progress; N. Bedard to follow up with A. Ristau to see if tiles were replaced
| 2021-10-01 |  | Additional ceiling tiles need to be replaced. Department to place W/O. KP
| 2022-05-12 |  | Dylan to follow up and see if a work order was ever placed
| 2022-06-30 |  | Nate to follow up on work order.
3 |  | Bike Racks |  | Exterior | Completed
| 2017-10-20 |  | Bike racks are needed - students are locking their bikes to inappropriate areas, ex. Dumpster
| 2018-11-01 |  | Unresolved; C. Bridgeman entered project requet as of 02/19/18 Update: Project with UPDC/in progress
| 2019-03-07 |  | CKB following up with UPDC. Location specified by DMD target summer 2019 for installation
| 2019-09-19 |  | In progress; N. Bedard to follow up
| 2020-01-02 |  | CKB to put another project request in
| 2022-05-12 |  | CKB submitted another project request form
| 2022-05-19 |  | Facilities is working on this, Nate to follow up.
| 2022-06-30 |  | Colleen passed the funding to facilities and the location has been identified. Project should finish up this summer.
4 | IPE | Metal Bulletin boards installation is proposal |  | Bishop First Floor Hallway | Completed
| 2019-10-08 |  | Metal bulletin boards installation is incomplete. Wooden boards mounted on south side hallway are crooked. They need to be leveled and metal sheathing needs to be installed Waiting since early August Is HVAC going to get replace? - isolation implemented Micky Gorman f/u complete project
| 2020-01-02 |  | Installed, need to get straightened, f/u with micky if anyone went back to fix it
| 2020-10-20 |  | Nate: Complete KP
5 | ILT | Sound proofing |  | Bishop 138 - Film Studio | In progress
| 2019-10-08 |  | Needs blown in sound proofing in ceiling, space is currently unusable as a film sound studio. Needs a way to turn off air handler during filming sessions, as currently unusable as a film sound studio Studio cannot be used f/u with Nate on progress with vibration augmentation - need new roof mechanic unit, not able to function with the noise Alishaa to schedule meeting between CKB, N. Bedard, Heather, (anyone else Nate and Heather would like to invite) need for sound proofing and cabinetry in basement level
| 2019-10-30 |  | Bishop center: ventilation, soundproofing meeting
| 2020-01-02 |  | Need a f/u meeting at Bishop
| 2021-08-09 |  | Meeting with Colleen, T Haskell, H Elliott-Famularo, M Toomey M Vertefeuille to discuss. KP
| 2021-10-08 |  | Colleen: UPDC is in the process of contracting a firm to come in and perform an acoustical study on multiple studios and practice rooms. The contract bid and award process should conclude in the Oct/Nov timeframe. KP
| 2022-05-12 |  | Acoustical study was complete. Mitigation of recommended renovations are in progress. Meeting to review results with department in progress.
6 | S | Card reader issues |  | Bishop 138 & 139 - Film & Mocap Studio | Completed
| 2019-10-08 |  | Triggering alarms to police when we key in, or prop doors from inside. Needs to change the silent alarm logic & triggers to have a proper use of space. We need to be able to open main hallway doors and prop open at times
| 2020-01-02 |  | Stacy Webb and Michael Toomey had Genetc training Genetec software to be installed by 1/22/20
| 2020-10-20 |  | Completed KP
7 | S | Furniture Request |  | Bishop First Floor Main Entry lobby | Completed
| 2019-10-08 |  | Need furniture for students and visitors in building to sit. Currently students sit on the floor in lobby while waiting Alishaa: work with student staff to get an inventory of items to fill the space from central stores (lobby items and couches)
| 2019-12-12 |  | Central stores did not have any lobby items, nor couches
| 2020-01-02 |  | CKB to look into purchasing furniture
| 2021-09-07 |  | Kate: Email sent to Heather with surplus information/hours. KP
| 2022-05-12 |  | Completed Winter of 2021
8 | ILT | HVAC Issues |  | Bishop 243 - Michael Vertefeuille Office | In progress
| 2019-10-08 |  | Air conditioning noise is unbearable in faculty offices on 2nd floor Related to existing items HVAC in both DMD and AAH requests, roof project A/C redo in Bishop
| 2020-01-02 |  | Alishaa to schedule a f/u meeting for HVAC/Bishop
| 2020-10-15 |  | Note out to M. Toomey to see if issue has resolved. KP
| 2022-05-16 |  | Nate will follow up with Michael Toomey
| 2022-05-19 |  | Per email with Micahel, the roof is leaking and has not been resolved. Still loud. May be addressed in upcoming acoustical study review
| 2022-05-24 |  | No changes. Acoustical study will potentially solve some of these problems. But also lack of funding for a new unit. Michael & Stacy will continue to place WOs as leaks occur so they can be patched.
| 2022-06-30 |  | Per Nate Michael is meeting with Mark Davis and Mike Toomey to look at issues. Nate will send Kate an update on the date of the walkthru.
| 2022-11-02 |  | Per Nate Walk thru notes: Various rooms on 1st floor have no heat. Bishop 243 still very loud due to unit noise.
9 | ILT | Sound dampening panel installation proposal |  | Bishop 138 - Film Studio | In progress
| 2019-10-08 |  | Purchase and install floor to ceiling height black, white and green curtains on dual curtain track so that it can be used as a film studio
| 2020-01-02 |  | Test if it could be fix
| 2020-02-12 |  | Still really noisy, inherit to space, open ceiling Looking to slow down the drive on the fan. Will potentially get an acoustician to evaluate the space, and determine the best solution, maybe spray installation in rafter Facility is taking the lead in checking for vendors
| 2022-05-12 |  | Acoustical study was complete. Mitigation of recommended renovations are in progress. Meeting to review results with department in progress.
10 | S | Lighting Issue |  | Bishop 138 - Film Studio/Bishop 139 MoCap Studio | Completed
| 2019-10-08 |  | Current 2 way automated lights are dangerous as installed. Room is completely black and full of equipment. Lights need to operate with simple on/off switch, not motion detector or timer Dangerous to have lights coming off and on in dark room - light switch on each door, move around to activate motion - easier to put on and off without sensor Get rid of sensor Heather to put work order in
| 2020-01-02 |  | Michael Toomey f/u if lighting WO is in
| 2020-10-20 |  | Note out to M. Toomey. Waiting on Response. KP
| 2022-05-12 |  | Nate will follow up with Michael Toomey
| 2022-05-24 |  | Michael Toomey said this work was completed during pandemic.
11 | ILT | Lighting Issue |  | Bishop 006/005/007 | Completed
| 2019-10-08 |  | Dimmable CAN lights need to be replaced with LED bulbs Work order to submit
| 2020-01-02 |  | Michael Toomey f/u if lighting WO is in
| 2020-10-20 |  | Note out to M. Toomey. Waiting on Response. KP
| 2022-05-12 |  | Nate will follow up with Michael Toomey
| 2022-05-24 |  | Michael Toomey said this work was completed during pandemic.
12 | ILT | Lack of temperature control |  | Various rooms on 1st fl | In progress - Facilities to follow up
| 2019-10-08 |  | Need WO from Heather No damper in - freezing, second floor has damper Alishaa to schedule meeting between CKB, Peter McQueeney, N.Bedard, Glen, Heather regarding temperature in building and DMD space expansion
| 2019-10-30 |  | Meeting at Bishop center regarding temperature
| 2020-01-02 |  | N.Bedard will check if Peter put workorder in
| 2022-05-12 |  | Nate will follow up with Michael Toomey
| 2022-06-30 |  | Will address durning HVAC walkthru.
13 | ILT | Faulty rooftop mechanicals |  | Bishop 2nd floor Cigna Room | On Hold
| 2016-10-06 |  | Airflow and boilder room noise rendering the Cigna innovation lab space unusable for students and faculty. Is there a short - term fix to the noise prior to the roof replacement project Roof will have 300 sq. ft of restoration in Spring 2017. They will cut oout and replace the bad section of the roof. They will work to find out the sound cause during replacement and work to mitigate the sound or resolve completely
| 2017-03-23 |  | Roof mechanicals have been turned up. A sound/vibration consultant will be brought in to confirm if more can be done with noise. Send for contractor, there will be no HVAC or roof replacement
| 2017-03-23 |  | Continuation of painting effort in faculty offices
| 2018-11-01 |  | Unresolved; C. Bridgeman entered project requet as of 02/19/18. Update: 11/1/18; Close-out on facilities issues document; Bishop Center converted to a UPDC project. Per Aug 2018 meeting with UPDC (M. Groza), roof to be replaced summer 2020; current scope includes replacement of roof membrane and replacement of HVAC/mechanicals
| 2018-11-16 |  | Roof project on hold indefinitely. UPDC to confirm latest timeline
| 2019-03-07 |  | Roof project on hold indefinitely. UPDC to confirm latest timeline
| 2022-06-30 |  | No change.
14 | ILT | HVAC Mechanical Issues |  | Bishop 146, 007, 005 | In progress
| 2016-10-06 | 717982, 725215, 729951, 729659 | HVAC issues: this semester we had a compressor failure for room 146 that lasted a few weeks during the beginning of the semester. After that was fixed, we lost AC in room 007 (which has computers and no windows and gets very hot). Next, we lost AC in room 005, then the hallway in the basement last week and during open house this weekend. Now no A/C on the 2nd floor HVAC cannot be replaced. Would need at least 6 months to complete all new ductwork and zone control within building. Tony Weston will arrange meeting with Tim & egineers to discuss HVAC remedies. Colleen & Cora Lynn will also attend
| 2017-03-27 |  | Will get quote for split unit stabilized for now but it's been cool. Replacement of ceiling tiles in Rm. 146; P. McQueeney will walk with Aris to review ceiling tiles issues in Bishop
| 2017-10-20 |  | Can we close?
| 2018-11-01 |  | TBD; need to confirm with DMD if issues resolved
| 2018-11-16 |  | TBD; need to confirm with DMD if issues resolved
| 2019-03-07 |  | TBD; need to confirm with DMD if issues resolved
| 2019-09-19 |  | Completed
| 2020-01-02 |  | Alishaa to meet with CKB to get notes from Bishop/HVAC meeting
| 2020-02-12 |  | Room 132: Facility change event, shut off, relocate center of room - resolved Downstream issue to other room 135, room is too loud Room 119 > resolved
| 2020-10-20 |  | Note out to M. Toomey. Waiting on response. KP
| 2022-05-12 |  | Nate will follow up with Michael Toomey.
| 2022-06-30 |  | From Nates notes: Mike Toomey noted that 146 has no cooling. 007 to hot. 005 no cooling. KP
15 | ILT | HVAC Mechanical Issues |  | Bishop Basement | Completed
| 2017-03-23 |  | The 4-5 heat pumps located in the ceilings above the DMD hallway work space. These often leak and fail on a fairly regular basis requiring us to remove much of our equipment located in that hallway space in support of facilities work on those pumps Basement pumps have been greased and updated. They will look to replace and change out with space renovation when completed on first floor
| 2017-10-20 |  | Can we close?
| 2018-11-01 |  | TBD, Need to confirm with DMD if issues resolved
| 2018-11-16 |  | TBD; need to confirm with DMD if issues resolved
| 2019-03-07 |  | TBD; need to confirm with DMD if issues resolved
| 2019-09-19 |  | Completed
16 |  | Painting restoration proposal |  | Bishop 1st Floor First Lobby | Completed
| 2017-03-27 |  | Can be completed during 1st floor renovation over summer 2018
| 2018-11-01 |  | C. Bridgeman / J. Johnston to ensure that it is in the queue. Update 11/1/18: per D. Koehler renovation can be incorporated into 1st floor space expansion project. C. Bridgeman to follow up with Academic Renovations
| 2019-03-07 |  | Issue rectified; project complete. Close out w/facilities
| 2019-09-19 |  | Completed
17 |  | Lighting Issue |  | Bishop Bathroom | Completed
| 2017-03-27 |  | Bathroom lighting and stall don’t work Place a WO with FacOps to have addressed
| 2018-11-01 |  | TBD; need to confirm with DMD if issues resolved
| 2018-11-16 |  | TBD; need to confirm with DMD if issues resolved
| 2019-03-07 |  | TBD; need to confirm with DMD if issues resolved
| 2019-09-19 |  | Completed
18 |  | Cleaning restoration |  | Bishop | Completed
| 2018-11-16 |  | Request for cleaning of Air Vents DMD is requesting someone to come and look at this issue. Colleen has correspondence regarding this that she will forward to facilities
| 2019-03-07 |  | Issue rectified; project complete. Close out w/facilities
| 2019-09-19 |  | Completed
19 |  | Door alarms |  | Bishop center | Completed
| 2019-10-08 |  | Addressed via Genetec training and elimination of key override and door propping.

## Jorgensen
Jorgensen
| Priority | Description |  | Area/Building/Room | Status
1 | SIPE | Lighting issues |  | Lower Jorgensen Fly Rail | Completed
| 2018-11-16 |  | Please send emails to facilities
| 2021-08-18 |  | Nate Bedard was brought up to speed on the rigging inspection report. Ed plans to speak with inspector over report findings and will set up a time to do a walk thru with Nate.
| 2022-05-12 |  | SFA Project in Progress to resolve issue as part of rigging system 6/30 Ed Weingard heading. No change. Fully funded.
Project Complete. Close-out
2 |  | Carpet replacement proposal |  | Jorgensen Auditorium Hall | Completed
| 2019-10-08 |  | Carpets are old and warped and creating a tripping hazard for our patrons and guest of the Jorgensen Aiming to get this completed by winter break Alishaa to schedule meeting between Pete Dunnak, Rodd Rock, CKB, N.Bedard, Antoaneta Fedeles, Mike Jednak
| 2020-01-02 |  | Pete was working on pricing with Tom
| 2021-10-01 |  | New carpet installed. KP
3 | IPE | Exterior Doors |  | Jorgensen: North and West side of the Building | In progress- facilties to follow up on
| 2018-11-16 |  | When exterior doors were painted and had hard-ware replacement, weather stripping was removed from the doors. Weather stripping is requested to be replaced before Winter. Facilities will check in on this matter believes the West Exterior Door recently had weather stripping replaced
| 2019-03-07 |  | OK; complete per R. Rock
| 2019-09-19 |  | N/A
| 2020-01-02 |  | Rodd Rock - weather stripping was failing, they got replaced but an again, heavy door N.Bedard to discuss with Micky about it (work with Rodd Rock and Gary)
| 2021-10-01 |  | Weather stripping replaced. Nate will check with Micky on upgrading door closers. KP
| 2022-05-12 |  | Nate will follow up with carpentry to confirm there is nothing else that can be done to closers
| 2022-05-25 |  | Carpentry was out today assessing the situation. Weather striping is needed to be replaced. Nate will follow up on the rest of the assessments
| 2022-06-30 |  | Per Nate: Met with carpentry, door closers adjusted, weather stripping has been replaced. W/O closed. Nate will talk to Rich and Mickey about getting a quote for a slider option.
4 | IPE | Energy consultation (check dramatic) |  | Jorgensen Stage lighting | On Hold
| 2017-03-23 |  | Instrument are old and need to be replaced Dave Maclntosh from Eversource will complete a replenishment study
| 2017-03-27 |  | Scope of project replacement qualifies for a huge rebate - intensity of color is not there
| 2017-10-20 |  | Currently collaborating with Dramatic Arts department on the Energy Consultation and theatrical lighting upgrade initiate. Also, pursuing funding though GUF committee
| 2018-11-01 |  | Upgrade as of 11/1/18 project in progress with Mike Demers. Current status: (1) Reidentifying project requirements, scope and venues (2) Soliciting lighting evaluation and cost benefit analysis with vendor (3) Facilitating discussions with Uconn's Energy Management/Facilities team regarding latest proposal and Eversource current rebate recovery program
| 2018-03-07 |  | Mike D. is in progress of completing an updated engineering study, which would require the following information compiled: 1) The installation cost for each location of the equipment we wish to purchase 2) Number, wattage and type of existing fixtures use (on average) for each location 3) Number of operating hours a year for existing fixtures at each location 4) Number, wattage and type of new fixtures for each new location. Follow up meetings with: Energy Management, Capital Budget & Planning and Provost Office are required once study is complete and cost benefit is reevaluated
| 2019-09-19 |  | Unresolved: CKB to follow up w/ M. Demers to determine status
| 2022-04-28 |  | On hold indefinitley due to budget
| 2022-11-17 |  | CKB checking with Facilities Operations: Incandescent bulbs for these fixtures are no longer being made. In addition, some fixtures utilize glass gels which are also no longer being produced. Once our current inventory of these incandescent bulbs/glass gels is liquidated, the old incandescent lighting fixtures will become obsolete.
5 | S | Exterior Lighting |  | Jorgensen | Completed
| 2016-10-06 | WO:646389 | Receive many complaints that it is difficult to see at night - Approaching and leaving the facility. Safety hazard Landscape Architect will review. Could be included into NW Science Quad project
| 2017-03-23 |  | Jorgensen patron fell as a result of poor lighting. Patron's condition was very serious and was taken away in ambulance. Facilities will complete a lighting survey, and will review upgrading to LED lights
| 2017-03-27 |  | Spotlights on roof are LED. FacOps have identified 3 areas to install better lighting
| 2017-10-20 |  | Eric K. - plan to light up stairs & add new lighting to overhang Theater spotlight - 1 was installed as a test. If Rod is happy they'll continue lighting, but will not go over Gant project w/ Eileen McHigh lighting isn't part of scope of project
| 2018-11-01 |  | Completed; Closed out
| 2019-03-07 |  | N/A
| 2019-09-19 |  | N/A
6 | IPE | Water Infiltration |  | Jorgensen South East Stair Well | Completed
| 2018-11-16 |  | Should be buttoned up by winter
| 2019-03-07 |  | Jay to follow up
| 2019-09-19 |  | In progress: N. Bedard to follow up to confirm/add weather stripping
| 2020-01-02 |  | Confrimed no current leaks through this door
7 |  | Roof Replacement |  | Jorgensen Main Roof | Unresolved
| 2022-05-25 |  | Main roof is leaking. Façade also in need of getting reapointed. Roof leaks are getting into exterior wall. Mike J said facilities will look into funding
| 2022-06-09 |  | Nate to follow up with Mike Jednak regarding status of funding/time table of roof project.
| 2022-06-30 |  | Still on hold due to funding.
9 |  | Auditorium House Light Replacement |  | Main House lights | Unresolved
| 2022-05-25 |  | Original to building, minor upgrades have happened already. Roughly 300 lights total but 1/2 replaced to LED (and the original lights are still in place. Only bulbs have been changed). New dimmers also needed. Stan Nolan said they will expidite this and do a walkthrough. Higher ones can be access via catwalks. Stan and Gary to set up meeting
| 2022-06-09 |  | Nate to follow up with Stan Nolan on status and plan. 6/30 Nate will f/u with stan for update.
10 |  | Water Fountain Replacement |  | Back Jorgensen | Unresolved
| 2022-05-25 |  | 10 fountains original to building have been covered with plastic. None are functioning but are plumbed. Gary can set up a walkthrough with plumbing to assess and get quote/feasibility of project. They would need chillers
| 2022-06-09 |  | Nate to enter work order and will initiate meeting for walk-through
| 2022-06-30 |  | Plumbing did a walk thru with Gary. Waiting on quote.
11 |  | Carpet Replacement Mezz & Lower Lobbies |  | Jorgensen | In Progress
| 2022-05-25 |  | Second floor mezz and lower lobbies have older carpeting that hasn't been replaced. Second floor runs into the women's restrooms and is bubbling and causing a saftey conern. Colleen suggests a meeting for ideas and walkthroughs & selection of carpeting.
| 2022-11-18 |  | CKB entered project request to replace lower and upper lobbies of the Jorgensen. Project assigned to Academic Renovations/T. Reichardt
| 2022-12-05 |  | CKB and T. Reichardt met with Gary and Rod to determine project scope. Carpet to be replaced in upper lobby (mezzanine level) and lower level lobby. Possibly some repainting in both areas, but lighting replacement. Depending on budget, could proect budget could carry flooring replacement in lower level gallery.
12 |  | Bathroom Stall Replacement |  | Jorgensen | Unresolved
| 2022-05-25 |  | Not all have been replaced. Gary/Rod need to give a total.
| 2022-06-09 |  | CKB to follow up w/ Gary and Rod (also read Jorg backup detail below)
13 |  | Carpet in Main Office |  | Jorgensen | Unresolved
| 2022-05-25 |  | replacement of carpeting in the main office
| 2022-06-09 |  | Add-in to project request above for lobby carpet
14 |  | Old Costume Shop Renovation |  | Jorgensen | Unresolved
| 2022-05-25 |  | Would like this space to turn into dressing Rooms. Mike suggested cubicals with doors that don't go up to full ceiling and are easy to move. Nate to work on getting a quote
| 2022-06-09 |  | Nate to follow up w/ Dave Kohler for guidance on entering project request or going straight to furniture vendor.
15 |  | Floor Replacement/Abatment |  | Tech Office, Gallery Storage Room, Sound Closet | Unresolved
| 2022-05-25 |  | flooring is cracking and tiles need to be reabaited and new tile needed. Asbestos Tile 9X9 are breaking. Nate will set up a meeting to determine priority, cost & time
| 2022-06-09 |  | Nate to schedule meeting w/ Jen Pescha for evaluation of asbestos abatement.
| 2022-06-30 |  | Nate spoke with Jen, all of the tiles left are not a hazard. No short term plan to replace. On radar to be included in future project as needed.
16 |  | Window Replacement |  | Tech Office, Backstage Dressing Rooms, Auditoriam Green Room | Unresolved
| 2022-05-25 |  | All are old swing out windows. Some places have been replaced and these are left. Nate to put in a work order to determine cost
| 2022-06-09 |  | Nate to enter work order and will initiate meeting for walk-through (CKB)
17 |  | Remodeling & Updating |  | Dressing Rooms, Costume Room, Theatre Classroom, Ladies Dressing Room, Elevator, Lower Lobby | Unresolved
| 2022-05-25 |  | Colleen would like to schedule a meeting to determine priorites and updating some spaces with new paint, tile ect. Some spaces are very outdated and or original to the building.
| 2022-06-30 |  | Building: • Building needs a new roof • Building needs the exterior brick to be repointed • Parking lot need to be resurfaced • Auditorium needs house lights replaced • Replace drinking fountains throughout building • Front doors cannot be safely secured, need either replacement or improved hardware Interior: • New carpeting in the Mezz and Lower Lobbies • Replace all the remaining old bathroom stalls • New carpet in the main offices • Not sure what the old costume shop will be used for but if we want to convert that to dressing rooms, maybe that could be added. • Also, the main doors to the hall need new weather stripping again. Tech Office/Backstage • Tech Office needs a floor abatement and replacement • Tech Office needs new ceiling and lighting • Tech Office needs new windows • Sound closet needs floor and wall abatement and replacement • Backstage dressing rooms need a remodel, Costume Room, Theater classroom and Ladies Dressing Rooms • Replace all windows backstage in dressing rooms • Replace windows in the Auditorium Green Room Gallery: • Gallery storage room needs floor abatement and replacement
Gallery:
· Gallery storage room needs floor abatement and replacement

## Benton
Benton
| Priority | Description |  | Area/Building/Room | Status
1 | High, S | Plumbing issues |  | Benton | Completed
| 2019-10-08 |  | The floor in the upstairs bathroom needs to get replaced. There is a punky area that is about to break through where the toilet tank leak was Staff bathroom, toliet issue keep leaking Get anything to help fall through Need to get work order in
| 2020-01-02 | WO#191211-143708 | N.Bedard - E-mailed for update
| 2020-01-10 |  | Toilet removed, new floor installed, toilet put back in
| 2020-10-20 |  | Complete KP
2 | High, S | Security bars on lower windows |  | Benton | Completed
| 2019-10-08 |  | We need bars installed on the lower - level windows as a safety/security issue Make it more secure - limited to public Can be anywhere (inside/outside) - can be done inside (easier) Nancy: put in work order: bars to be installed inside Also Nancy to reach out to public safety regarding safety access in case of an emergency
| 2020-01-02 |  | Alishaa to f/u with Nancy and remind her to place a work order in
| 2020-10-19 |  | Complete. KP
3 | IPE | Painting Restoration |  | Benton | Completed
| 2019-10-08 |  | The wall outside the elevator - lobby level - needs painting. We had brought this up a couple of years ago but it never got done
| 2020-01-02 | WO# 191211-143709 | Assinged 12/17/2019
| 2020-10-19 |  | Per Nate: Complete - KP
4 | IPE | Window washing |  | Benton | Completed
| 2019-10-08 |  | The front windows need washing from the outside
| 2020-01-02 |  | This is not part of typical cleaning provided. Can wash as billable. Place WO in to get estimate as needed. KP
5 |  | Light issues |  | Gallery | In progress
| 2016-10-06 |  | Light switches - will need to crnfinuty proof LED's Nancy will purchase - contrary to do reimbursement Eric Krueger addressed light switch transition to one breaker that has matching switch plates and dimmers
| 2017-03-23 |  | Goal is have computerized electrical panel - possibly summer 2017
| 2017-03-27 |  | Nancy and Kerry - will confirm type of LED's to Benton needs. Eric Krueger will check on reimbursement for previously purchased LED lights
| 2017-10-20 |  | Some don't work/switches overall need to be upgrade and uninformed. Computerized electrical panel needs to be implemented
| 2018-11-01 |  | Unresolved; need update from facilities
| 2018-11-16 |  | Unresolved; need update from facilities
| 2018-03-07 |  | Unresolved; need update from facilities
| 2019-09-19 |  | Unresolved; need update from facilities
| 2020-01-02 |  | LED lights were installed, panels needs to be implemeneted
| 2022-05-12 |  | Nate emailed Rachel Z, meeting walkthrough scheduled for 5/24/22, to see which option will be best 6/30 Nate did a walk thru with Rachel. Quoting new panel. Nate will update Kate with the timeline.
| 2022-06-30 |  | Nate did a walk thru with Rachel. Quoting new panel.
| 2022-11-17 |  | Facilites is planning to replace as part of the fiscal 24 budget. KP
6 | S | New restroom installation proposal |  | Benton Museum | Completed
| 2018-11-16 |  | Shares a space with the Beanery Coffee Shop and the Benton Bathrooms are used by their patrons. However, they are also taking over the front desk area and the sculpture atrium when the Museum is closed. They would like to close the gate between the shop and museum when museum is closed, however that would required the Beanery to acquire their own restrooms It was suggested to add signage in the Interim and Colleen encourages to speak about this further offline. Facilities has suggested a Project Request to get started on the conversation of new, separate restrooms facilities
| 2018-03-07 |  | CKB to follow up with Anne
| 2019-09-19 |  | Unresolved; lack of funding to resolve
| 2020-01-02 |  | Place project order in to get estimate
| 2021-08-15 |  | Nate Bedard and Colleen did a walk thru of the space. Nate presented possible new layouts for the space. Project order placed for estimate. KP
| 2022-05-12 |  | Project in progress to add new access in Beanery Café which will reroute patrons around the Benton lobby when the museum is closed. Plan will will eliminate access to the reception area completely which will rectify safety and risk outside of operating hours.
| 2022-11-17 |  | Project completed; close-out
7 | IPE | Water infiltration |  | B-5 Mechanical Room | Completed
| 2016-10-06 |  | Wall waterproofing and floor drainage to better protect collection storage during pipe leaks Has a history of repetitive leaks. Creating curtain drains/cutting a groove in concrete cloud mitigate draining issues
| 2017-03-23 |  | Peter McQueeney to complete evaluation on 3/24
| 2017-03-27 |  | Peter McQueeney /FacOps will replace a condensate pipe to prevent leaking
| 2017-10-20 |  | Can we close? Resolved per Nancy, Pete McQueeney is checking
| 2018-11-01 |  | Completed, closed out
| 2018-11-16 |  | N/A
| 2019-03-07 |  | N/A
| 2019-09-19 |  | N/A
8 | IPE | HVAC system issue |  | All Areas | Completed
| 2016-10-06 |  | Continued routine maintenance on HVAC systems especially units that affect galleries and collection storage Gilman has been at 50% humidity - Rachel/John can confirm, not fully mitigated
| 2017-03-23 |  | Humidifer for Gilman Gallery is in quoting process
| 2017-10-20 |  | Still an ongoing issue. Not always at 50% humidity
| 2018-11-01 |  | Unresolved; need update from facilities
| 2019-03-07 |  | TBD; need to confirm with the Benton that issue has been recitifed HVAC SOP has been developed to ensure proper workflow and museum best practices and standard operating procedures are being followed
| 2019-09-19 |  | Completed
9 | IPE | Landscaping issue |  | Parking lot/dock | Completed
| 2016-10-06 |  | Loading dock and parking area has become a garbage dump central for all neighboring buildings Aris to check in with Bob Flowers to see if vertipack machines can be used in place of current dumpster
| 2017-03-27 |  | Aris to check with Bob Flowers to see if new vertipacks can be coordinated with new patio at the Benton
| 2017-10-20 |  | Reduced # of cans. Aris explored compactor but electricity associated posed financial challenges. Nancy seems to notice an improvement and it's been cleaner
| 2018-11-01 |  | Completed; close out
| 2018-11-16 |  | N/A
| 2019-03-07 |  | N/A
| 2019-09-19 |  | N/A
10 | IPE | Security Assessment Mitigation |  | Benton Museum | Completed
| 2016-10-06 |  | Specialized security needed for galleries. Project request form compelted. Coordinating security consultants from museums through Chuck Brome Awaiting sign off on vendors and will request proposals for security system installation
| 2017-03-27 |  | Eric Kruger will work with Chuck Brome to coordinate security for Benton and light switches
| 2017-10-20 |  | Colleen attended conference regarding security. Security Director from Harvard Art Museum will be visiting Uconn for security assessment. Nancy has Melissa Frank (legal) liaison Uconn's policy doesn’t include art insurance. Divided by exhibit & permanent. (Within Hartford insurance Umbrella)
| 2018-11-01 |  | Per C. Bridgeman - mitiation strategy in place
| 2018-11-16 |  | Per C. Bridgeman - mitiation strategy in place
| 2019-03-07 |  | Per C. Bridgeman - mitiation strategy in place
| 2019-09-19 |  | Completed
11 | IPE | Replacement carpet to hardwood or composite |  | Benton Gallery | Completed
| 2017-03-27 |  | Summer 2017 - Pete will be getting a quote
| 2017-10-20 |  | Meeting is scheduled with Pete Dunnack and Benton team to discuss options and evaluate needs on 11/2/17. 2 or 3 galleries. Center and East gallery, East Gallery concerned about sound mitigation
| 2018-11-01 |  | Completed, closed out
| 2018-11-16 |  | N/A
| 2019-03-07 |  | N/A
| 2019-09-19 |  | Completed
12 | S | Exit Doors |  | East Gallery | Completed
| 2017-10-20 |  | Fire Marshall established that one of the exit doors in the East Gallery is unnecessary and they're going to remove the exit
| 2018-11-01 |  | Completed; close out
| 2018-11-16 |  | N/A
| 2019-03-07 |  | N/A
| 2019-09-19 |  | Completed
13 |  | Access to rooms for facilities or UITS |  | Benton Museum | Completed
| 2017-10-20 |  | Nancy wants to limit access to all rooms within the Benton to 3 staff members. Anyone who wants access will have to go through the 3 staff members, except in emergencies. Dean's office requesting keys to be included in master set
| 2018-11-01 |  | Completed, closed out
| 2018-11-16 |  | N/A
| 2019-03-07 |  | N/A
| 2019-09-19 |  | N/A
14 | IPE | Humidity Temperature installation |  | Benton Museum | Completed
| 2018-11-16 |  | There are humdity and temperature requirements for installations. On 11/15, the humidity and temperature dropped drastically and 3 HVAC Units were non-operational. Requesting some sort of alarm system when humidity/temperature/HVAC failures occur Seems to have stabilized, however, this issue still needs to be addressed for further occurences
| 2019-03-07 |  | OK; complete follow up meeting occurred with Glen Mathieu, Peter McQueeney, and Benton Staff; conclusion was to institute a standard operating procedure for future remediation of HVAC issues to better maintain and preserve the museum's collection. Benton developed and disseminated to Facilities Operations 3/7/19
| 2019-09-19 |  | Completed
15 | IPE | Landscaping |  | Benton | Completed
| 2019-10-08 |  | A few oak tree need trimming at the back of the museum (back patio) as the branches are almost touch the slate roof
| 2020-01-02 |  | One tree was removed, inspected and no current need to trim
| 2022-05-25 |  | Kerry Smith brought up in the facilities meeting more triming is needed on a regular basis. Aris said they will adjust trimming schedule. This will be an ongoing issues due to the sculptre in the patio being covered by trees/bushes
| 2022-06-30 |  | Karen and Aris have a plan in place. They will grow back and landscaping will trim them.
16 |  | Electrical Issue |  | Benton | Completed
| 2019-10-08 |  | Carey - exposed electrical wire, other side of retaining wall - black wires sticking out - out worker in last wires sticking out - put workorder in last year - erosion caused this - there was a cone Micky Gorman: Facilities, will have someone look into it Will trim trees and clean up
| 2020-01-02 |  | Complete
17 |  | Benton K-12 Teaching/Conf Room Renovation/Remodel |  | Benton | In progress
| 2022-11-18 |  | CKB entered UPDC project request. BENTON RM 106 currently being used as conference/catering area, but would like to redesign for multi-purpose K-12 educational/meeting space.
| 2022-12-05 |  | T. Reichardt assigned to the project. Plans to meet with stakeholders to determine scope.

## BIMP
Ballard Institute & Museum of Puppetry
| Priority | Description |  | Area/Building/Room | Status
1 | ILT, S | Safety/Security Issue |  | Depot Campus | Completed
| 2019-10-08 |  | Workers set off alarms because they're given keys (from locksmith) to the Depot Campus Building, but are not told the spaces have security alarms which are armed - sudden alarm notices interrupt work and office hour. Sometimes don't call Ballard. Takes about half hour to reset, Safety/Security issue: no indentification on who is to do a job, etc. don't want to be surprise Facilities departments and their vendors to make appointments to get into the Ballard Institute's Depot Campus Buildings Facility: Removes flexibility to get work done if scheduled Have alarm code so won't have to set off - weekend (students would have to try to deal with) Swipe, call to have access - manage access - someone to meet facilities out at building Workorder - permission slip to go into building (wear uniform, badge properly) Moving to Kirby - town police not UConn ** Will inform locksmith department regarding Willimantic and Bolton has to the alarm - Mansfield (no alarm) to provide cellphone number, and will work on a protocal (Eric K.)
| 2020-10-20 |  | Per Nate: Issues resolved due to new standard operating process that have been put in place. KP
2 | S | Cardreader issue |  | Exterior Doors | Completed
| 2016-10-06 |  | Emily has been working with facilities to resolve keyswipe issues
| 2017-03-27 |  | Has been addressed and should be all set
| 2017-10-20 |  | Keyswipe system continues to be problematic. Before 9AM studnts have issues with access. Schedule meeting with Dana in early AM to test. Could it be an issue with time change?
| 2018-11-01 |  | Unresolved; need update from BIMP/Facilities
| 2018-11-16 |  | Unresolved; need update from BIMP/Facilities
| 2019-04-18 |  | Unresolved; need update from BIMP/Facilities
| 2019-09-19 |  | Need update from the Ballard; has issue been resolved?
| 2020-01-02 |  | Ask Emily if issue was resolved, if not reference to Dana Dunnak
| 2021-08-15 |  | Resolved. KP
3 | IPE, A | Sanitary/plumbing issues |  | Ballard Institute | Completed
| 2017-10-20 |  | Plumbing issues in bathrooms - forced to shut down and close bathrooms continually. This is probably a design issue. Eric K will delegate work to Mike Rocchetti, FacOps mechanical engineer, to address. Handicap men's and women's not paper towels external to building. Meeting with Barnes and Noble team to manage access
| 2018-11-01 |  | Unresolved; need update from BIMP/Facilities
| 2018-11-16 |  | Unresolved; need meeting with Barnes and Noble to readdress operating procedure with respect to bathroom usage. Emily setting up meeting w/ B&N, CKB, and facilities to address continous issues and concerns
| 2019-04-18 |  | Unresolved; need meeting with Barnes and Noble to readdress operating procedure with respect to bathroom usage. Emily setting up meeting w/ B&N, CKB, and facilities to address continous issues and concerns
| 2019-09-19 |  | Need update from the Ballard; has issue been resolved?
| 2020-01-02 |  | f/u meeting. Colleen had meeting with Barnes and Noble and Custodial
f/u meeting. Colleen had meeting with Barnes and Noble and Custodial
| 2021-10-02 |  | Custodial Serviced meeting scheduled to discuss current issues. KP
| 2021-11-15 |  | Meeting was held in the Fall semester 2021 with representatives from the Ballard, B&N and Facilities Operations. Cleaning issues mitigated by varying schedule that would compliment operating schedule of the Ballard. If further cleanings are needed, CKB communicated that the Ballard should proceed with adding further cleanings to the schedule which would have to be contained with Ballard's budget. Ultimately the incremental cost would be worth it if it improves overall sanitation of bathrooms.
| 2022-05-12 |  | CKB to follow up with John/Emily to check in on progress
| 2022-05-25 |  | John to follow up with Emily to ensure this is complete, but he believes it is
| 2022-10-15 |  | Emily will enter W/Os as needed. KP
4 | HS, IPE | Pest Control |  | Depot Buildings, Willimantic and Bolton | Completed
| 2018-11-16 |  | Ongoing issue with mice in these spaces; poison traps have been set Place work orders to replac poison traps and place work order every time and occurrence happens
| 2019-04-18 |  | BIMP continues to monitor the mouse traps. Exterminator recommend putting traps around the perimeter of the exterior of the building, but that work is outside his contract with Uconn. Jay will contract Billy from Waltham to see of this is possible. Outside traps have been typically banned due to protected species policy
| 2019-09-19 |  | Need Update from Ballard, has issue need resolved?
| 2020-01-02 |  | f/u with Emily
| 2020-10-20 |  | Pest contractor out and areas treated. Confirm with Colleen/Emily. Note out to Emily to confirm. KP
| 2021-01-07 |  | Emily confirmed that pest contractor has treated areas and that there will be ongoing treatments as needed. KP
5 | A | Restroom maintenance |  | BIMP Restrooms | Completed
| 2018-11-16 |  | Hardware and hinges on restroom stalls need to be checked as temporary hinges are not working properly Work order has been placed for this new item. Facilities to follow up
| 2019-04-18 |  | Jay will touch base with Carpentry - hinges do take a wile to order
| 2019-09-19 |  | Need update from the Ballard; has issue been resolved?
| 2020-01-02 |  | Doors were corrected f/u with Emily Wicks
| 2020-10-20 |  | Completed. KP
6 | IPE | General cleanliness; shares a cleaning crew with B&N who are reportedly un-reliable. BIMP is requesting Uconn Facilities take over the space |  | BIMP Restrooms | Completed
| 2018-11-16 |  | Facilities is encouraging BIMP to check their lease and see what is required of the cleaning crew. First step is to hold the contracted party accountable and facilities is willing to lend a hand in this area. The suggestion was also made to limit who uses the restrooms via master key
| 2019-04-18 |  | BIMP still having cleanliness issues. They met with the new manager of the cleaning company, and he said he would work with Len and us to create a clear list of items to be done. Issues are unresolved. Emily to schedule meeting w/ B&N, CKB, and Facilities to address cleaning issues and develop standard operating procedures
| 2019-09-19 |  | Need update from Ballard; has issue need resolved based on latest meeting w/ custodial manager?
| 2020-10-20 |  | No current issues. Emily will complete work orders as issues arise. KP
7 | IPE | HVAC/Humidity control continues to be an issue |  | BIMP Vestibule | Completed
| 2018-11-16 |  | A alarm system has been requested to let the staff know when the HVAC goes out so they may place work orders. Facilities will follow up on this issue
| 2019-04-18 |  | April 10 - Productive meeting with Mike Rocchetti and Newman Architects to review Ballard HVAC issues. Newman to conduct a site visit to evaluate space; recommend HVAC consultant with museum preservation experience and include plans for remediation with their poposal; expected in about 3 weeks
| 2019-09-19 |  | HVAC project put on hold indefinitely due to funding; meeting is scheduled w. FacOps HVAC area to develop Standard Operating Procedures to mitigate as much as possible HVAC/Humidity control issues until larger HVAC renovation can occur
| 2020-01-02 |  | Get update from Glenn Alishaa 1:1 with CKB to get notes from BIMP/HVAC meeting
| 2020-10-20 |  | Glenn and Pete bought system to enhance the existing mechanicals. Note to Emily to submit work orders as needed. KP
8 |  |  |  | Emergency Exit | Completed
| 2017-10-20 |  | Exit keeps blinking - faulty wiring? Emily has entered two WO's for them
| 2018-11-01 |  | Unresolved; need update from Facilities
| 2018-11-16 |  | Unresolved; need update from BIMP/Public Safety
| 2019-04-18 |  | Unresolved; need update from BIMP/Public Safety
| 2019-09-19 |  | Unresolved; need update from BIMP/Public Safety
| 2020-01-02 |  | f/u with Emily Wicks
| 2020-10-19 |  | Note to Emily to see if this is still an issue. Waiting on response. Resolved
9 |  | Security cameras |  | BIMP | Completed
| 2017-10-20 |  | Barnes & Noble take cameras off same unit as BIMP. Piggyback off of Benton's meeting with Harvard Security. Colleen and Emily will meet with them afterwards. Will follow up with sales manager from B&N - break away from their system
| 2018-11-01 |  | Unresolved; need update from facilities
| 2018-11-16 |  | Unresolved; need update from BIMP/Public Safety
| 2019-04-18 |  | Unresolved; need update from BIMP/Public Safety
| 2019-09-19 |  | Completed
10 |  | Access to storage |  | Merrit Cottage | Completed
| 2017-10-20 |  | Bart needs access to storage
| 2018-11-01 |  | Completed; closed out
| 2018-11-16 |  | N/A
| 2019-04-18 |  | N/A
11 | S | Security cameras access |  | BIMP | Completed
| 2018-11-16 |  | He is going to try to get a vendor in over there next few weeks to determine if new cameras are needed or if they existing cameras can be reconfigured. Detective Hanna is creating a report
| 2019-04-18 |  | Work has been done on the security system in last couple of weeks, no confirmation as to whether it is offically on the Uconn system Emily to follow up
| 2019-09-19 |  | Completed
12 | IPE | Fan is not working |  | BIMP Museum Space | Completed
| 2018-11-16 |  | New item; work order placed
| 2019-04-18 |  | OK; complete per Emily Wicks
| 2019-09-19 |  | Completed
13 | IPE | Ceiling Panels in the lobby and gallery are water-damaged and need to be replaced |  | BIMP Lobby and Gallery | Completed
| 2018-11-16 |  | Working with Carpentry and replacement should occur within the next week or so.
| 2019-04-18 |  | OK; complete per Emily Wicks
| 2019-09-19 |  | Completed
14 | IPE | HVAC upgrade proposal |  | Willimantic, Mansfield, & Bolton Cottages | Completed
| 2016-10-06 |  | Storage, temperature control concerns for collections. Data loggers at Depot to see what the humdity and temperature is like and then we can see if a humidity system is necessary Long term solution needs further discussion to address improved climiate control, better facility monitoring and adequate space for incoming donated collections
| 2017-03-27 |  | Can be resolved from a "Nest" unit Eric Kruger - Order nest units to monitor humidity control
| 2017-10-20 |  | Eric Kruger is unsure if they installed alarm to test temperature or industrail monitor. Nest units are really for domestic areas. Enter WO
| 2018-11-01 |  | Unresolved; need update from facilities. Update 11/1/18: C. Bridgeman working with UPDC on alternative storage locations more suitable for collections storage
| 2018-11-16 |  | Unresolved; need update from facilities. Update 11/1/18: C. Bridgeman working with UPDC on alternative storage locations more suitable for collections storage
| 2019-09-19 |  | In progress: Kirby lease currently w/General Counsel's office; UPDC reviewed scope with architect and will send to SFA for review along with project scheduled. Stakeholder visit will be scheduled in October
| 2020-01-02 |  | Long term move to Kirby Mills
15 |  | On Going Leaks/Stained Tile |  | BIMP Museum Space | Unresolved
| 2022-05-25 |  | The Oaks are leaking several times a year in the Museum Space. Museum has closed several times. The Oaks can't figure out where leaks are (seems to be coming for apartments above). This is causing tiles to stain as well.
| 2022-06-30 |  | Emily will work with leasing manager on any new issues. Colleen would like to discuss preventative measures. Kate to reach out to John and Emily to get a feel for flooding issues.
| 2022-08-19 |  | Per Emily no leaks since July, but nothing has been done that would prevent a leak going forward. The Oaks team offered to inspect above our ceiling every few weeks, but that is quite tricky with our exhibit in place. Kyle Muncy, who handles university partnerships and was at the meeting with the Oaks and the property manager, reached out to me because the university's lease for these Downtown Storrs spaces is up in 15 months. He would like the property owners to be more proactive, so I think the university is hoping to include this as part of their lease negotiations.
16 |  | Lighting |  | BIMP Hallways | Unresolved
| 2022-05-25 |  | Back hallway if theatre and back hall shared with Barnes & Noble have burnt out over head lights. Back hallway of theatre has 3 total sets, 2 are out and the shared hallway is similar. Multiple WOs have been placed, no progress.
| 2022-06-30 |  | Colleen would like to see the lease. Nate will check on ownership of this item.
17 |  | Painting |  | BIMP Museum Space | Unresolved
| 2022-05-25 |  | Walls need to be repainted due to leaks and new museum displays.
| 2022-06-30 |  | Nate will check with John Cooke on the status of this item. Property manager item?